## Abstract (hidden)
S. No. | Name of the Agency | No.of ULBs | Total Quantity Awarded (in MT) | Total Quantity remediated till date (in MT) | Balance Quantity (in MT) | % of work | Required Rate of Progress (in MT) | Quantity remediated per day (in MT)
1 | 2 |  | 3 | 4 | 5 | 6
1 | M/s Tharuni Assosiates & Avinash agency, Guntur | 85 | 1914267.31 | 640341.75 | 1273925.56 | 33.45% | 13201.8435 | #REF!
2 | M/s Zigma global Enviro Solutions Private limited, Erode | 26 | 1440437 | 203278 | 1237159 | 14.11% | 9934.0483 | #REF!
3 | M/s Saurashtra Enviro private limited, Gujarat | 11 | 314825 | 95388 | 219437 | 30.3% | 2171.2069 | 2252.19
4 | M/s Sudhakar Infra Pvt.Ltd. | 1 | 63550 | 63550 | 0 | 100% | 1412.2222 | 944.11
| Total | 123 | 3733079.31 | 1002557.75 | 2730521.56 | 26.86% | 26719.3209 | #REF!

## Abstract (3)
Agency Wise Legacy Waste Status Abstract as on 16.06.2025
S. No. |  | Name of the Agency | No.of ULBs | Total Quantity Awarded (in MT) | CumulativeQuantity remediated till date (in MT) | Balance Quantity (in MT) | % of work Comp. | Required rate of progress per day to complete by 2nd October 2025 (in MT) | No.of Machines Functioning | Capacity of the Functioning Machines (in MT) | Quantity remediated on 14.05.2025 (in MT) | Quantity remediated on 15.05.2025 (in MT) | Quantity remediated on 14.05.2025 (in MT) | Quantity remediated on 13.05.2025 (in MT) | Quantity remediated on 12.05.2025 (in MT) | Quantity remediated on 16.05.2025 (in MT) | Quantity remediated on 17.05.2025 (in MT) | Quantity remediated on 18.05.2025 (in MT) | Quantity remediated on 19.05.2025 (in MT) | Quantity remediated on 20.05.2025 (in MT) | Quantity remediated on 21.05.2025 (in MT) | Quantity remediated on 22.05.2025 (in MT) | Quantity remediated on 23.05.2025 (in MT) | Quantity remediated on 24.05.2025 (in MT) | Quantity remediated on 25.05.2025 (in MT) | Quantity remediated on 26.05.2025 (in MT) | Quantity remediated on 27.05.2025 (in MT) | Quantity remediated on 28.05.2025 (in MT) | Quantity remediated on 29.05.2025 (in MT) | Quantity remediated on 30.05.2025 (in MT) | Quantity remediated on 31.05.2025 (in MT) | Quantity remediated on 01.06.2025 (in MT) | Quantity remediated on 02.06.2025 (in MT) | Quantity remediated on 03.06.2025 (in MT) | Quantity remediated on 04.06.2025 (in MT) | Quantity remediated on 05.06.2025 (in MT) | Quantity remediated on 06.06.2025 (in MT) | Quantity remediated on 07.06.2025 (in MT) | Quantity remediated on 08.06.2025 (in MT) | Quantity remediated on 09.06.2025 (in MT) | Quantity remediated on 10.06.2025 (in MT) | Quantity remediated on 11.06.2025 (in MT) | Quantity remediated on 12.06.2025 (in MT) | Quantity remediated on 13.06.2025 (in MT) | Quantity remediated on 14.06.2025 (in MT) | Quantity remediated on 15.06.2025 (in MT)
1 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 11 | 12 | 11 | 11 | 12 | 13 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 13 | 11 | 11 | 11 | 11 | 12 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12
1 | 1a | M/s Tharuni Assosiates, Guntur | 19 | 1279152 | 169490.53 | 1109661.47 | 13.25% | 12329.5719 | 15 | 12600 | 3566.255 | 665.43 | 3131.6 | #REF! | #REF! | 3131.6 | 3587.09 | 4308.67 | 4467 | 897.51 | 1887.17 | 1436.29 | 2088.75 | 3524.16 | 3191.64 | 3146.51 | 3299.13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 5868.69 | 7224.94 | 4886.73 | 2708.92 | 6062.41
| 1b | Coastline (ELURU Cluster) | 8 | 158462 | 2978 | 155484 | 1.879% | 1727.6 | 2 | 1440 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.37 | 346.79 | 179.76 | 0 | 0 | 0 | 86.21 | 0 | 237.93 | 0 | 276.83 | 330.94 | 626.68 | 660.08
| 1c | (KADAPA Cluster) | 9 | 219004 | 0 | 219004 | 0% | 2433.3778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1d | Srinivas (HINDUPUR Cluster) | 6 | 116561 | 2473.99 | 114087.01 | 2.122% | 1267.6334 | 2 | 1400 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141.4 | 578 | 421.71 | 452.94 | 935.25 | 0 | 0 | 0
| 1e | Srinivas Setty (ADDANKI Cluster) | 9 | 237910 | 11159 | 226751 | 4.69% | 2519.4556 | 2 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244.46 | 339.99 | 406.04 | 631.72 | 584 | 235.77 | 905.74 | 746.5 | 286.03 | 719.73 | 727.71 | 203.33 | 394.73 | 210.15 | 818.33 | 1097.98 | 1039.67 | 1153.95 | 812.42
| 1f | V.Raju | 4 | 111074 | 317 | 110757 | 0.2854% | 1230.6333 | 1 | 600 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sub Total | 55 | 2122163 | 186418.52 | 1935744.48 | 8.784% | 21508.272 | 22 | 17640 | 3566.255 | 665.43 | 3131.6 | #REF! | #REF! | 3131.6 | 3587.09 | 4308.67 | 4467 | 897.51 | 1887.17 | 1436.29 | 2088.75 | 3524.16 | 3191.64 | 3146.51 | 3299.13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 7139.96 | 9535 | 6257.34 | 4489.55 | 7534.91
2 |  | M/s Zigma global Enviro Solutions Private limited, Erode | 26 | 1440437 | 203278 | 1237159 | 14.11% | 13746.2111 | 8 | 5500 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 4930.69 | 4801.55 | 3115.38 | 3782.8 | 3741.75
3 | 3 | M/s Saurashtra Enviro private limited, Gujarat | 11 | 314825 | 95388 | 219437 | 30.3% | 2438.1889 | 3 | 4200 | 1845.245 | 1652.39 | 2722.4 | 2252.19 | 1642.23 | 2722.4 | 2521.17 | 740.04 | 3168.58 | 2996.92 | 2403.355 | 1746.335 | 2609.6 | 2322.565 | 2468.515 | 1241.78 | 2138.605 | 3162.43 | 2118.2 | 2826.2 | 4055.59 | 2873.53 | 2854.24 | 873.09 | 2126.18 | 3518.835 | 3064.02 | 2484.07 | 1723.55 | 1050.765 | 2027.99 | 1435.5 | 606.77 | 0 | 0 | 0
|  | New Clusters Total | 92 | 3877425 | 485084.52 | 3392340.48 | 12.51% | 37692.672 | 33 | 27340 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 13506.15 | 14943.32 | 9372.72 | 8272.35 | 11276.66
1 |  | M/s Tharuni Assosiates & Avinash agency, Guntur (Old) | 30 | 635115.31 | 489773.81 | 145341.5 | 77.12% | 1709.9 | 6 | 4100 | 267.82 | 415.83 | 781.29 | #REF! | #REF! | 781.29 | 1159.76 | 917.71 | 0 | 750.88 | 0 | 0 | 0 | 474.44 | 158.84 | 293.33 | 692.23 | 690.15 | 843.83 | 348.36 | 1773.66 | 474.22 | 348.91 | 529.51 | 311.62 | 874.93 | 0 | 479.63 | 0 | 0 | 0 | 484.9 | 686.01 | 0 | 0 | 600.22
2 |  | M/s Sudhakar Infra Pvt.Ltd. | 1 | 63550 | 63550 | 0 | 100% | 0 | 0 | 0 | 936.32 | 767 | 0 | 944.11 | 896.94 | 0 | 485.33 | 582.88 | 800.16 | 0 | 0 | 0 | 836.52 | 160.26 | 927.64 | 906.95 | 873.77 | 941.03 | 834.03 | 890.14 | 834.89 | 890.27 | 925.66 | 926.74 | 678.98 | 950.54 | 739.61 | 178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Old Clusters Total | 31 | 698665.31 | 553323.81 | 145341.5 | 79.2% | 1709.9 | 6 | 4100 | 1204.14 | 1182.83 | 781.29 | #REF! | #REF! | 781.29 | 1645.09 | 1500.59 | 800.16 | 750.88 | 0 | 0 | 836.52 | 634.7 | 1086.48 | 1200.28 | 1566 | 1631.18 | 1677.86 | 1238.5 | 2608.55 | 1364.49 | 1274.57 | 1456.25 | 990.6 | 1825.47 | 739.61 | 657.63 | 0 | 0 | 0 | 484.9 | 686.01 | 0 | 0 | 600.22
|  | Grand Total | 123 | 4576090.31 | 1038408.33 | 3537681.98 | 22.69% | 39402.572 | 39 | 31440 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 13991.05 | 15629.33 | 9372.72 | 8272.35 | 11876.88
*Note |  | M/s Tharuni Assosiates, Guntur | 49 | 1914267.31 | 659264.34 | 1255002.97 | 34.44% | 14039.4719 | 21 | 16700 |  |  |  | #REF! | #REF!
*Note |  | M/s Tharuni Assosiates, Guntur and Sub- Contractor s | 81 | 2646204.31 | 675875.33 | 1970328.98 | 25.54% | 21987.5387 | 27 | 21140 |  |  |  | #REF! | #REF!

## Abstract (2) (hidden)
Agency Wise Legacy Waste Status Abstract as on 13.05.2025
S. No. | Name of the Agency | No.of ULBs | Total Quantity Awarded (in MT) | Total Quantity remediated till date (in MT) | Balance Quantity (in MT) | % of work | Required rate of progress per day to complete by 2nd October 2025 (in MT) | No.of Machines Functioning | Capacity of the Functioning Machines (in MT) | Quantity remediated Today (in MT)
1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | M/s Tharuni Assosiates, Guntur | 55 | 2122163 | #REF! | #REF! | #REF! | 14737.2431 | 8 | 6900 | #REF!
2 | M/s Zigma global Enviro Solutions Private limited, Erode | 26 | 1440437 | 203278 | 1237159 | 14.11% | 10003.0347 | 2 | 2100 | #REF!
3 | M/s Saurashtra Enviro private limited, Gujarat | 11 | 314825 | 95388 | 219437 | 30.3% | 2186.2847 | 2 | 3600 | 2252.19
| New Clusters Total | 92 | 3877425 | #REF! | #REF! | #REF! | 26926.5625 | 12 | 12600 | #REF!
1 | M/s Tharuni Assosiates & Avinash agency, Guntur (Old) | 30 | 635115.31 | 470851.22 | 164264.09 | 74.14% | 4410.523 | 5 | 3500 | #REF!
2 | M/s Sudhakar Infra Pvt.Ltd. | 1 | 63555 | 63550 | 5 | 99.99% | 441.3542 | 2 | 1300 | 944.11
| Old Clusters Total | 31 | 698670.31 | 534401.22 | 164269.09 | 76.49% | 4851.8772 | 7 | 4800 | #REF!
| Grand Total | 123 | 4576095.31 | #REF! | #REF! | #REF! | 31778.4397 | 19 | 17400 | #REF!
*Note | M/s Tharuni Assosiates, Guntur | 85 | 2757278.31 | #REF! | #REF! | #REF! | 19147.766 | 13 | 10400 | #REF!

## Tharuni Associates
Agency Wise Legacy Waste Status Abstract as on 25.05.2025 | Agency Wise Legacy Waste Details
Agency | Agency | Cluster | S.no | ULB | Quantity to be remediated in MT | Cumulative Quantity remediated till date in MT | Balance Quantity in MT | % of Comp. | Capacity of Machine per day to be installed (in MT) | No of Machines | Machine No | Daily capacity | Start date | No-of days requred for Completion | Expected date of completion | Quantity remediated on 12.05.2025 (in MT) | Quantity remediated on 13.05.2025 (in MT) | Quantity remediated on 14.05.2025 (in MT) | Quantity remediated on 15.05.2025 (in MT) | Quantity remediated on 16.05.2025 (in MT) | Quantity remediated on 21.05.2025 (in MT) | Quantity remediated on 17.05.2025 (in MT) | Quantity remediated on 18.05.2025 (in MT) | Quantity remediated on 19.05.2025 (in MT) | Quantity remediated on 20.05.2025 (in MT) | Quantity remediated on 21.05.2025 (in MT) | Quantity remediated on 22.05.2025 (in MT) | Quantity remediated on 23.05.2025 (in MT) | Quantity remediated on 24.05.2025 (in MT) | Quantity remediated on 25.05.2025 (in MT) | Quantity remediated on 26.05.2025 (in MT) | Quantity remediated on 27.05.2025 (in MT) | Quantity remediated on 28.05.25 (in MT) | Quantity remediated on 29.05.25 (in MT) | Quantity remediated on 30.05.25 (in MT) | Quantity remediated on 31.05.25 (in MT) | Quantity remediated on 01.06.25 (in MT) | Quantity remediated on 02.06.25 (in MT) | Quantity remediated on 03.06.25 (in MT) | Quantity remediated on 04.06.25 (in MT) | Quantity remediated on 05.06.25 (in MT) | Quantity remediated on 06.06.25 (in MT) | Quantity remediated on 07.06.25 (in MT) | Quantity remediated on 08.06.25 (in MT) | Quantity remediated on 09.06.25 (in MT) | Quantity remediated on 10.06.25 (in MT) | Quantity remediated on 11.06.25 (in MT) | Quantity remediated on 12.06.25 (in MT) | Quantity remediated on 13.06.25 (in MT) | Quantity remediated on 14.06.25 (in MT) | Quantity remediated on 15.06.25 (in MT) | Remarks | 30th April 2025 | 4th May 2025 | 5th May 2025 | 6th May 2025 | 7th May 2025 | 8th May 2025 | 1st May to 8th 2025 | Status
1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 10 | 11 | 12 | 13 | 14 | 16 | 16 | 16 | 16 | 17 | 17 | 16 | 16 | 16 | 16 | 16 | 16 | 15 | 15 | 16 | 15 | 16 | 15 | 15 | 15 | 15 | 16 | 17 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 16 |  | 15 | 16 | 17 | 21 | 24 | 25 |  | 26 | 27 | 28 | 20
M/s Tharuni Associates | M/s Tharuni Assosiates, Guntur | Kadapa Municipal Corporation | 1 | Kadapa | 400000 | 71242 | 328758 | 17.81% | 4200 | 3 | M1 | 900 | 2025-05-06 | 147 | 2025-09-30 | 1204.46 | 1393.96 | 1690.28 | 0 | 1720.23 | 1720.23 | 1573.9 | 1628.98 | 2084.6 | 897.51 | 1468.01 | 1436.29 | 1923.2 | 1841.97 | 1570.91 | 1255.14 | 1641.07 | 2239.81 | 2553.17 | 1064.05 | 1793.37 | 2117.28 | 2108.03 | 2609.36 | 2280.87 | 1568 | 2241.38 | 2721.43 | 2846.4 | 2368.04 | 2056.58 | 1783.52 | 2947.69 | 2137.97 | 1513.2 | 2663.3 | M1 functioning | 0 | [5 empty] | 0 | Work not yet started (Agency is awaiting for permission from municipality's to inauguration and start the work.)
[11 empty] | M2 | 1100 | 2025-05-06 |  | 2025-09-30 | [36 empty] | M2 functioning
[11 empty] | M3 | 800 | 2025-05-25 |  | 2025-09-30 | [36 empty] | M3 Functioning
[11 empty] | M11 | 1400 | 2025-06-16 |  | 2025-09-30 | [36 empty] | M11 arrived at site
| M/s Tharuni Assosiates, Guntur | Rajahmundry, Cluster (3 ULBs) | 2 | Srikakulam | 80978 | 24493 | 56485 | 30.25% | 2100 | 2 | M4 | 800 | 2025-05-05 | 60 | 2025-07-30 | 429.655 | 376.715 | 230.505 | 0 | 698 | 698 | 1397.42 | 1860.19 | 1589.41 | 0 | 0 | 0 | 0 | 862.88 | 833.17 | 629.69 | 0 | 0 | 0 | 0 | 535.5 | 299.14 | 536.17 | 1026.97 | 839.22 | 418.61 | 0 | 0 | 0 | 0 | 0 | 669.38 | 673.82 | 256.82 | 0 | 0 | Work in progress | [7 empty] | Work on Hold (Inauguration is Completeed )
[11 empty] | M5a | 700 | 2025-05-09 |  | 2025-07-30 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 700.48 | 660.305 | 410.85 | 612.95 | 0 | 0 | 0 | 0 | 0 |  | 834.06 |  | 0 | 0 | Work in progress
[11 empty] | M5b | 600 | 2025-05-30 |  | 2025-07-30 | [34 empty] | 0 | 0 | Work in progress
|  |  | 3 | Vizianagaram | 30604 | 20555.56 | 10048.44 | 67.17% | 800 | 1 | M6 | 800 | 2025-04-26 | 50 | 2025-06-30 | 117.1 | 661.21 | 722.93 | 562.75 | 378.93 | 378.93 | 577.32 | 601.69 | 662.3 | 0 | 0 | 0 | 0 | 566.8 | 787.56 | 813.6 | 515.87 | 0 | 0 | 0 | 0 | 0 | 0 | 831.37 | 765.99 | 829.94 | 532.59 | 484.98 | 408.22 | 670.07 | 354.71 | 593.7 | 0 |  |  |  | Work on hold due to rain
|  |  | 4 | Rajahmundry | 76735 | 3023.63 | 73711.37 | 3.94% | 900 | 1 | M7 | 900 | 2025-05-23 | 70 | 2025-09-30 | o | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165.55 | 0 | 0 | 0 | 56.92 | 308.3 | 354.22 | 328.71 | 0 | 0 | 0 | 482.49 | 0 | 0 | 340 | 0 | 0 | 289.24 | 475.56 | 0 | 387.63 |  |  |  | Work in progress
|  | Total |  |  | 188317 | 48072.19 | 140244.81 | 25.53% | 6 | 4100 | 5 | 3800 |  |  |  | 546.755 | 1037.925 | 953.435 | 562.75 | 1076.93 | 1076.93 | 1974.74 | 2461.88 | 2251.71 | 0 | 0 | 0 | 165.55 | 1429.68 | 1620.73 | 1443.29 | 572.79 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1263.08 | 1895.51 | 256.82 | 0 | 0 |  | 0
| M/s Tharuni Assosiates, Guntur | Kakinada, Cluster | 5 | Kakinada | 300000 | 15454 | 284546 | 5.151% | 3400 | 3 | M9 | 900 | 2025-05-26 | 127 | 2025-09-30 | 212.31 | 233.16 | 202.38 | 0 | 334.44 | 334.44 | 38.45 | 217.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147.99 | 280.46 | 332.32 | 249.07 | 257.08 | 203.33 | 375.9 | 869.4 | 347.19 | 701.42 | 1044.38 | 0 | 602.06 | 798.18 | 746.56 | 1816.79 | 1957.01 | 1089.01 | 145.37 | 1684.83 | Work is in progress | [7 empty] | 1. Trail run Completed. 2.Processing of Legacy waste to be started.
[11 empty] | M10 | 1100 | 2025-05-05 |  | 2025-09-30 | [36 empty] | Work is in progress
[11 empty] | M10a | 1400 | 2025-06-30 |  | 2025-09-30 | [36 empty] | New machine to be deployed of Capacity 1400MT to achive the target quantity.
|  |  | 6 | Amalapuram | 27543 | 1601.34 | 25941.66 | 5.814% | 600 | 1 | M12 | 600 | 2025-05-11 | 50 | 2025-09-30 | 335.21 | 354.83 | 261.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320.59 | 0 | 0 | 143 | 0 | 0 | 0 | 0 | Work in progress with previous material | [7 empty] | Work not yet started (Agency is awaiting for permission from municipality's to inauguration and start the work.)
|  | Total |  |  | 327543 | 17055.34 | 310487.66 | 5.207% | 4000 | 4 | 4 | 4000 |  |  |  | 547.52 | 587.99 | 463.42 | 0 | 334.44 | 334.44 | 38.45 | 217.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147.99 | 280.46 | 332.32 | 249.07 | 257.08 | 203.33 | 375.9 | 869.4 | 347.19 | 701.42 | 1044.38 | 0 | 922.65 | 798.18 | 746.56 | 1959.79 | 1957.01 | 1089.01 | 145.37 | 1684.83 |  | 0
| M/s Tharuni Assosiates, Guntur | Chilakaluripeta, Cluster (13 ULBs) | 7 | Chilakaluripet | 166278 | 8450 | 157828 | 5.082% | 800 | 1 | M14 | 800 | 2025-05-19 | 90 | 2025-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.69 | 0 | 419.16 | 0 | 0 | 252.51 | 0 | 448.08 | 480.07 | 295.98 | 405.36 | 238.14 | 0 | 0 | 0 | 446.84 | 295.92 | 391.25 | 332.27 | 422.58 | 389.39 | 531.32 | 681.78 | 507 | 0 | 644.4 | 594.01 | 543.42 | Work on hold due to rain
[9 empty] | 800 |  | M6(M/C) |  | 2025-07-15 |  | 2025-09-30 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | New machine to be deployed of Capacity 800MT
[11 empty] | M15(M/C) |  | 2025-08-01 |  | 2025-09-30 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | M/c will be shifted from Bapatla
|  |  | 8 | Guntur | 43811 | 22204 | 21607 | 50.68% | 900 | 1 | M13 | 900 | 2025-04-09 | 40 | 2025-09-30 | 0 | 334.37 | 350.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457.21 | 509.72 | 0 | 0 | 0 | 0 | 545.07 | 1257.32 | 498.6 | 512.59 | 879.81 | 389.43 | 754.36 | 602.94 | 1044.95 | 0 | 262.9 | 454.7 | 0 | 667.46 | Work in progress
|  |  | 9 | Ponnuru | 8376 | 0 | 8376 | 0% |  |  | M13 (S) |  | 2025-07-15 | 15 | 2025-07-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Ponnuru material 8376MT will be shifted to Guntur
|  |  | 10 | Narsaraopet | 30609 | 0 | 30609 | 0% | 800 |  | M26 |  | 2025-06-17 | 60 | 2025-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Machine Installation completed.Waiting for Inaugaration
|  |  | 11 | Piduguralla | 10793 | 0 | 10793 | 0% |  |  | M26(S) |  | 2025-08-01 | 30 | 2025-08-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Piduguralla Material 10793MT will be shifted to Narasaraopet
|  |  | 12 | Vinukonda | 11195 | 0 | 11195 | 0% |  |  | M26(S) |  | 2025-09-01 | 30 | 2025-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Vinukonda Material 11195MT will be shifted to Narasaraopet
|  |  | 13 | Bapatla | 46264 | 1828 | 44436 | 3.951% | 1400 | 1 | M15 | 1400 | 2025-05-14 | 40 | 2025-07-30 | 0 | 0 | 109.03 | 102.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124.91 | 0 | 0 | 0 | 0 | 0 | 0 | 303.32 | 231 | 0 | 303.83 | 301.46 | 354.96 | Work on hold due to rain
|  |  | 14 | Repalle | 7203 | 0 | 7203 | 0% |  |  | M15 (S) |  | 2025-09-01 | 10 | 2025-09-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Repalle material 7203MT will be shifted to Bapatla
|  |  | 15 | Macherla | 30894 | 639 | 30255 | 2.068% | 600 | 1 | M16 | 600 | 2025-06-10 | 60 | 2025-07-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49.86 | 124.3 | 161.83 | 0 | 154.88 | 148.44 | Work in progress
|  |  | 16 | Dachepalli | 6194 | 0 | 6194 | 0% |  |  | M16(s) |  | 2025-09-01 | 15 | 2025-07-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Dachepalli Material 6194MT will be shifted to Macherla
|  |  | 17 | Gurazala | 1675 | 0 | 1675 | 0% |  |  | M16(s) |  | 2025-09-01 | 10 | 2025-09-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Gurazala Material 1675MT will be shifted to Macherla
|  |  | 18 | Sattena-palle | 0 | 0 | 0 | - |  |  | - |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 19 | Mangalagiri Tadepalli | 0 | 0 | 0 | - |  |  | - |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  |  |  | 363292 | 33121 | 330171 | 9.117% | 5300 | 4 | 5 | 3700 |  |  |  | 0 | 334.37 | 459.12 | 102.68 | 0 | 0 | 0 | 0 | 130.69 | 0 | 419.16 | 0 | 0 | 252.51 | 0 | 448.08 | 937.28 | 805.7 | 405.36 | 238.14 | 0 | 0 | 545.07 | 1829.07 | 794.52 | 903.84 | 1212.08 | 812.01 | 1143.75 | 1134.26 | 2079.91 | 862.3 | 424.73 | 1402.93 | 1050.35 | 1714.28 |  | 0
| New Clusters Total |  |  |  | 1279152 | 169490.53 | 1109661.47 | 13.25% | 13506 | 4111 | 1800 | 15700 |  |  |  | 2298.735 | 3354.245 | 3566.255 | 665.43 | 3131.6 | 3131.6 | 3587.09 | 4308.67 | 4467 | 897.51 | 1887.17 | 1436.29 | 2088.75 | 3524.16 | 3191.64 | 3146.51 | 3299.13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 5868.69 | 7224.94 | 4886.73 | 2708.92 | 6062.41
| M/s Tharuni Assosiates, Guntur | Cluster 01 | 1 | Yelamanchili | 8719 | 8719 | 0 |  | - | - | - | - | - | - | - | - | - | [34 empty] | Work Completed | - | - | - | - | - | - | 0 | 0 | 0 | 0
|  | Cluster 01 | 2 | Pithapuram | 24910 | 24910 | 0 |  | - | - | - | - | - | - | - | - | - | [34 empty] | Work Completed | - | - | - | - | - | - | 0 | 0 | 0 | 0
|  | Cluster 01 | 3 | Peddapuram | 19612 | 19612 | 0 |  | - | - | - | - | - | - | - | - | - | [34 empty] | Work Completed | - | - | - | - | - | - | 0 | 0 | 0 | 0
|  | Cluster 01 | 4 | Rajam | 12849.14 | 12849.14 | 0 |  | - | - | - | - | - | - | - | - | - | [34 empty] | Work Completed | - | - | - | - | - | - | 0 | 0 | 0 | 0
|  | Cluster 01 | 5 | Tuni | 22097.82 | 22097.82 | 0 |  | - | - | M25 | - | - | - | - | - | - | [34 empty] | Work Completed | - | - | - | - | - | - | 0 | 0 | 0 | 0
|  | Cluster 01 | 6 | Samalkot | 37786 | 37786 | 0 |  | - | - | M26 | - | - | - | - | - | - | [34 empty] | Work Completed | - | - | - | - | - | - | 0 | 0 | 0 | 0
|  | Cluster 01 | 7 | Bobbili | 14711 | 12946.88 | 1764.12 |  |  | 1 | M24 | 600 | - |  | 30.05.2025 | 0 | 121.15 | [34 empty] | Work in progress | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 01 | 8 | Gollaprolu NP | 13135 | 10889.71 | 2245.29 |  |  | 1 | M8 | 600 |  |  | 30.05.2025 | 0 | 87.15 | [34 empty] | Work in progress | [6 empty] | 0 | 181.53 | 262.03 | 0
|  | Cluster 01 | 9 | Amadalavalasa | 6678.68 | 0 | 6678.68 |  |  |  | M4(S) | 800 | 20.06.2025 | 15 | 05.07.2025 | 0 | 0 | [34 empty] | Material will be shifted to Srikkulam |  |  | #VALUE! | 2025-09-30 | Qty will be Shifted to Srikakulam |  | 0 | 0 | 0 | 0
|  | Cluster 01 | 10 | Ichapuram | 6260 | 0 | 6260 |  |  |  | M4(S) | 800 | 20.06.2025 | 15 | 05.07.2025 | 0 | 0 | [34 empty] | Material will be shifted to Srikkulam |  |  | #VALUE! | 2025-09-30 | Qty will be Shifted to Srikakulam |  | 0 | 0 | 0 | 0
|  | Cluster 01 | 11 | Palasa -Kasibugga | 9625.88 | 0 | 9625.88 |  |  |  | M4(S) | 800 | 15.06.2025 | 20 | 05.07.2025 | 0 | 0 | [34 empty] | Material will be shifted to Srikkulam |  |  | #VALUE! | 2025-09-30 | Qty will be Shifted to Srikakulam |  | 0 | 0 | 0 | 0
|  | Cluster 01 | 12 | Parvathipuram | 11921.09 | 0 | 11921.09 |  |  |  | M24(S) | 600 | 01.06.2025 | 20 | 20.06.2025 | 0 | 0 | [34 empty] | Material will be shifted to Bobbili | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 01 | 13 | Salur | 12042 | 0 | 12042 |  |  |  | M24(S) | 600 | 15.06.2025 | 20 | 05.07.2025 | 0 | 0 | [34 empty] | Material will be shifted to Bobbili | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 01 | 14 | Palakonda | 7700 | 0 | 7700 |  |  |  | M4(S) | 800 | 15.06.2025 | 20 | 05.07.2025 | 0 | 0 | [34 empty] | Material will be shifted to Srikkulam |  |  | #VALUE! | 2025-09-30 | Qty will be Shifted to Srikakulam |  | 0 | 0 | 0 | 0
|  | Cluster 01 | 15 | Nellimarla | 7727.4 | 0 | 7727.4 |  |  |  | M6(S) | 800 | 2025-06-10 | 20 | 2025-06-30 | 0 | 0 | [34 empty] | Material will be shifted to Vizainagaram |  |  | 20 | 2025-06-30 | Qty will be Shifted to Vizianagaram |  | 0 | 0 | 0 | 0
|  | Cluster 01 | 16 | Narsipatnam | 6250 | 0 | 6250 |  |  |  | M25(S) | 600 | 15.05.2025 | 20 | 2025-06-30 | 0 | 0 | [34 empty] | Material Will be shifted to Tuni |  |  |  | 15.06.2025 |  |  | 0 | 0 | 0 | 0 | [5 empty] | Narsipatnam Material will be shifted to Tuni
[5 empty] | 222025.01 | 149810.55 | 72214.46 |  | 0 | 2 | 0 | 7000 | 2025-06-10 | 150 | 2150-12-30 | 0 | 208.3 | [34 empty] | 0 | 0 | 0 | #VALUE! | 229558 | 0 | 0 | 0 | 181.53 | 262.03 | 0 | 0 | 0 | 0 | 0 | 0
| M/s Tharuni Assosiates, Guntur | Cluster 02 | 17 | Nidadavole | 37207.27 | 37207.27 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [34 empty] | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 02 | 18 | Tanuku | 74206 | 74206 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [34 empty] | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 02 | 19 | Ramachandra-puram | 22142.68 | 0 | 22142.68 |  |  | 1 | M18 | 1100 |  |  | 01.07.2025 | 0 | 0 | [34 empty] | Work is in Progress | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 02 | 20 | Yeleswaram | 11022 | 0 | 11022 |  |  |  | M26(S) | 600 | 15.05.2025 |  | 10.06.2025 | 0 | 0 | [34 empty] | Material will be shifted to samalkota |  |  |  | 15.06.2025 |  |  | 0 | 0 | 0 | 0 | [5 empty] | Yelleswaram Material will be shifted to Samalkota
|  | Cluster 02 | 21 | Mandapeta | 8779 | 0 | 8779 |  |  |  | M18(S) | 1100 | 20.06.2025 |  | 01.07.2025 | 0 | 0 | [34 empty] | Material will be shifted to Ramchandra puram | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 02 | 22 | Mummidivaram | 5624 | 0 | 5624 |  |  |  | M12(S) | 600 | 2025-09-15 |  | 2025-09-30 | 0 | 0 | [34 empty] | Material will be shifted to Amalapuram |  |  | 15 | 2025-09-30 | Qty will be Shifted to Amalapuram |  | 0 | 0 | 0 | 0
[5 empty] | 158980.95 | 111413.27 | 47567.68 |  | 0 | 1 | 0 | 3400 |  | 0 |  | 0 | 0 | [34 empty] | 0 | 0 | 0 | 15 | 45930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Avinash agency | Cluster 03 | 23 | YSR Tadigadapa | 50000 | 50000 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [34 empty] | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 | 24 | Tiruvuru | 20842 | 20842 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [34 empty] | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 |  | Nuzvid | 15995 | 15995 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [34 empty] | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 |  | Kondapalli | 4925 | 4925 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [34 empty] | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 |  | Palacole | 25181 | 25181 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [34 empty] | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 |  | Kovvur | 8775.13 | 8775.13 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [34 empty] | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 |  | Amalapuram | 27910.22 | 27910.22 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [34 empty] | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 | 25 | Narsapur | 51312 | 39393.02 | 11918.98 |  | 600 | 1 | M27 | 600 |  |  | 30.09.2025 | 545.09 | 564.87 | [34 empty] | M27 is functioning |  |  |  | 15.07.2025 |  |  | 394.4 | 562.24 | 510.27 | 0 | [5 empty] | Work in progress
|  | Cluster 03 | 26 | Jangareddygudem | 18736 | 16606.03 | 2129.97 |  | 600 | 1 | M17 | 600 |  |  | 10.06.2025 | 0 | 0 | [34 empty] | Work in progress | [6 empty] | 0 | 210.47 | 0 | 0
|  | Cluster 03 | 27 | Akiveedu | 7312 | 0 | 7312 |  |  |  | M21(S) | 500 | 15.09.2025 | 15 | 30.09.2025 | 0 | 0 | [34 empty] | Material will be shifted to Bhimavaram |  |  | #VALUE! | 2025-09-30 |  |  | 0 | 0 | 0 | 0
|  | Cluster 03 | 28 | Chintalapudi | 7300 | 0 | 7300 |  |  |  | M17(S) |  | 25.05.2025 |  | 10.06.2025 | 0 | 0 | [34 empty] | Material will be shifted to Jangareddy Gudem | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 | 29 | Vuyyuru | 10000 | 0 | 10000 |  |  |  | M28(S) | 400 | 01.07.2025 |  | 30.07.2025 | 0 | 0 | [34 empty] | Material Will be shifted to Pedana |  |  |  | 31.07.2025 |  |  | 0 | 0 | 0 | 0 | [5 empty] | Vuyyuru material will be shifted to Pedana
|  | Cluster 03 | 30 | Pedana | 5821 | 0 | 5821 |  | 400 | 1 | M28 | 400 | 25.05.2025 |  | 10.07.2025 | 0 | 0 | [34 empty] | Erection Work in Progress |  |  |  | 30.06.2025 |  |  | 0 | 0 | 0 | 0 | [5 empty] | Erection Work in Progress
[5 empty] | 254109.35 | 209627.4 | 44481.95 |  | 1600 | 3 | 0 | 2500 | 0 | 15 | 0 | 545.09 | 564.87 | [34 empty] | 0 | 0 | 0 | #VALUE! | 45930 | 0 | 0 | 394.4 | 772.71 | 510.27 | 0 | 0 | 0 | 0 | 0 | 0
|  | Old clusters Total |  |  | 635115.31 | 470851.22 | 164264.09 |  | 1600 | 6 | 0 | 12900 |  |  |  | 545.09 | 773.17 | [34 empty] | 0 | 0 | 0 | #VALUE! | 321418 | 0 | 0 | 394.4 | 954.24 | 772.3 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grand Total |  |  | 1914267.31 | 640341.75 | 1273925.56 |  | 15106 | 4117 | 1800 | 28600 |  |  |  | 2843.825 | 4127.415

## Tharuni (hidden)
Legacy Waste Scheduled timelines for completion of total quantity before 2nd October 2025
Agency | Cluster | ULB | Quantity to be remediated (in MT) | Quantity remediated (in MT) | Quantity remediated upto 30th April (in MT) | Balance Quantity (in MT) | Capacity of Machine per day to be installed (in MT) | No of Machines | Details of Machinery | [8 empty] | Actual Quantity remediated per day (in MT) | No-of days requred for Completion | Expected date of completion | Remarks | 30th April 2025 | 1st May 2025 | 2nd May 2025 | 3rd May 2025 | 4th May 2025 | 5th May 2025 | 6th May 2025 | 7th May 2025 | 8th May 2025 | 1st May to 8th 2025 | Status
[9 empty] | Machine No | Daily capacity | Start date | Machine No | Daily capacity | Start date | Machine No | Daily capacity | Start date
1 | 2 | 3 | 4 | 5 | 5 | 6 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 21 | 22 | 23 | 24 | 25 |  | 26 | 27 | 28 | 20
M/s Tharuni Assosiates, Guntur
M/s Tharuni Associates | Kadapa Municipal Corporation | Kadapa | 400000 | 0 | 0 | 400000 | 2800 | 3 | M1 | 900 | 2025-05-01 | M2 | 1100 | 2025-05-01 | M3 | 800 | 2025-05-01 |  | 152 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0 | As per agency plan of Action Work should be started on 01 may 2025,But work not started.
| Srikakulam | Srikakulam | 80978 | 20.6 | 0 | 80957.4 | 1500 | 2 | M4 | 800 | 2025-05-01 | M5 | 700 | 2025-05-01 |  |  |  |  | 152 | 2025-09-30 |  | 0 | 20.6 | [7 empty] | 20.6 | Work is in Progress,but Processing material is less then the machine Capacity
|  | Ichapuram | 6260 | 0 | 0 | 6260 | [14 empty] | Qty will be Shifted to Srikakulam | 0 | 0 | [7 empty] | 0
|  | Palasa -Kasibugga | 9625.88 | 0 | 0 | 9625.88 | [14 empty] | Qty will be Shifted to Srikakulam | 0 | 0 | [7 empty] | 0
|  | Amadalavalasa | 6947 | 0 | 0 | 6947 | [14 empty] | Qty will be Shifted to Srikakulam | 0 | 0 | [7 empty] | 0
|  | Palakonda | 7700 | 0 | 0 | 7700 | [14 empty] | Qty will be Shifted to Srikakulam | 0 | 0 | [7 empty] | 0
| Total |  | 111510.88 | 20.6 | 0 | 111490.28 | [15 empty] | 0 | 20.6 | [7 empty] | 20.6
| Vizianagaram | Vizianagaram | 30604 | 3086.01 | 2828.35 | 27517.99 | 800 | 1 | M6 | 800 | 2025-04-26 | [7 empty] | 65 | 2025-06-30 |  | 280.18 | 257.66 | [7 empty] | 257.66 | Work is in Progress,but Processing material is less then the machine Capacity
|  | Nellimerla | 7727 | 0 | 0 | 7727 | [14 empty] | Qty will be Shifted to Vizianagaram | 0 | 0 | [7 empty] | 0
| Total |  | 38331 | 3086.01 | 2828.35 | 35244.99 | [15 empty] | 280.18 | 257.66 | [7 empty] | 257.66
| Rajahmundry | Rajahmundry | 76735 | 0 | 0 | 76735 | 1200 | 2 | M7 | 600 | 2025-05-15 | M8 | 600 | 2025-05-15 |  |  |  |  | 138 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0
|  | Kovvuru | 915 | 0 | 0 | 915 | [14 empty] | Qty will be Shifted to Rahahmundry | 0 | 0 | [7 empty] | 0
| Total |  | 77650 | 0 | 0 | 77650 | [15 empty] | 0 | 0 | [7 empty] | 0
| Kakinada | Kakinada | 300000 | 0 | 0 | 300000 | 3400 | 3 | M9 | 900 | 2025-05-01 | M10 | 1100 | 2025-05-01 | M11 | 1400 | 2025-05-15 |  | 152 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0 | Trail run Completed,Procedding of Legacy yet to start
| Amalapuram | Amalapuram | 27543 | 0 | 0 | 27543 | 600 | 1 | M12 | 600 | 2025-05-01 | [7 empty] | 152 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0 | As per agency plan of Action Work should be started on 01 may 2025,But work not started.
|  | Mumidivaram | 5624 | 0 | 0 | 5624 | [14 empty] | Mumidivaram Qty shifted to amalapuram | 0 | 0 | [7 empty] | 0
| Total |  | 33167 | 0 | 0 | 33167 | [15 empty] | 0 | 0 | [7 empty] | 0
| Guntur | Guntur | 43811 | 11998 | 11998 | 31813 | 900 | 1 | M13 | 900 | 2025-04-09 | [7 empty] | 174 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0
|  | Ponnur | 8376 | 0 | 0 | 8376 | [14 empty] | Ponnur Qty Shifted to Guntur | 0 | 0 | [7 empty] | 0
| Total |  | 52187 | 11998 | 11998 | 40189 | [15 empty] | 0 | 0 | [7 empty] | 0
| Chilakaluripet | Chilakaluripet | 166278 | 0 | 0 | 166278 | 1600 | 1 | M14 | 800 | 2025-05-05 | M6(M/C) | 800 | 2025-07-15 |  |  |  |  | 148 | 2025-09-30 | M6(M/C) shifted to Chilakaluripet | 0 | 0 | [7 empty] | 0
| Bapatla | Bapatla | 46264 | 0 | 0 | 46264 | 1400 | 1 | M15 | 1400 | 2025-05-01 | [7 empty] | 152 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0 | As per agency plan of Action Work should be started on 01 may 2025,But work not started.
|  | Repalle | 7203 | 0 | 0 | 7203 | [14 empty] | Repalle Qty shifted to Bapatla | 0 | 0 | [7 empty] | 0
| Total |  | 53467 | 0 | 0 | 53467 | [15 empty] | 0 | 0 | [7 empty] | 0
| Macherla | Macherla | 30894 | 0 | 0 | 30894 | 600 | 1 | M16 | 600 | 2025-05-25 | [7 empty] | 128 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0
|  | Gurazala | 1675 | 0 | 0 | 1675 | [14 empty] | Gurazal Qty shifted to Macherla | 0 | 0 | [7 empty] | 0
|  | Dachepalli | 6194 | 0 | 0 | 6194 | [14 empty] | Dachepalle Qty shifted to Macherla | 0 | 0 | [7 empty] | 0
| Total |  | 38763 | 0 | 0 | 38763 | [15 empty] | 0 | 0 | [7 empty] | 0
| Narasarao pet | Narasarao pet | 30609 | 0 | 0 | 30609 | 1700 | 2 | M17 | 600 | 2025-06-15 | M18 | 1100 | 2025-07-15 |  |  |  |  | 107 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0
|  | Vinukonda | 11195 | 0 | 0 | 11195 | [14 empty] | Vinukonda qty shifted to Narasaraopet | 0 | 0 | [7 empty] | 0
|  | Piduguralla | 10793 | 0 | 0 | 10793 | [14 empty] | Piduguralla qty shifted to Narasaraopet | 0 | 0 | [7 empty] | 0
| Total |  | 52597 | 0 | 0 | 52597 | [15 empty] | 0 | 0 | [7 empty] | 0
| Palacole | Palacole | 30000 | 0 | 0 | 30000 | 600 | 1 | M19 | 600 | 2025-05-15 | [7 empty] | 138 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0
| Bhimavaram | Bhimavaram | 32358 | 0 | 0 | 32358 | 1200 | 1 | M20 | 600 | 2025-07-15 | M21 | 600 | 2025-07-15 |  |  |  |  | 77 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0
|  | Akividu | 7312 | 0 | 0 | 7312 | [14 empty] | Akeevidu Qty shifted to Bhimavaram | 0 | 0 | [7 empty] | 0
| Total |  | 39670 | 0 | 0 | 39670 | [15 empty] | 0 | 0 | [7 empty] | 0
| Hindupur, Cluster (6 ULBs) | Hindupur | 49020 | 0 | 0 | 49020 | 700 | 1 | M25 | 700 | 2025-05-10 | [7 empty] | 143 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0
|  | Dharmavaram | 23000 | 0 | 0 | 23000 | 700 | 1 | M26 | 700 | 2025-05-10 | [7 empty] | 82 | 2025-07-31 |  | 0 | 0 | [7 empty] | 0
|  | Kadiri | 20000 | 0 | 0 | 20000 | 700 | 1 | M27 | 700 | 2025-05-10 | [7 empty] | 51 | 2025-06-30 |  | 0 | 0 | [7 empty] | 0
|  | Penukonda | 13578 | 0 | 0 | 13578 |  | 1 | M28 (M/C) | 700 | 2025-06-25 | [7 empty] | 67 | 2025-08-31 | M28(M/C) shifted from Puttaparty | 0 | 0 | [7 empty] | 0
|  | Puttaparthy | 10299 | 0 | 0 | 10299 |  | 1 | M28 | 700 | 2025-05-10 | [7 empty] | 36 | 2025-06-15 |  | 0 | 0 | [7 empty] | 0
|  | Madakasira | 664 | 0 | 0 | 664 |  | 1 | M27 (M/C) | 700 | 2025-07-15 | [7 empty] | 5 | 2025-07-20 | M27(M/C) shifted from Kadiri | 0 | 0 | [7 empty] | 0
| Total |  | 116561 | 0 | 0 | 116561 | 2100 | [14 empty] | 0 | 0 | [7 empty] | 0
| Per day Capacity | [5 empty] | 20400 | [23 empty] | 0
| Addanki, Cluster (9 ULBs) | Ongole | 61929 | 0 | 0 | 61929 | 900 | 1 | K1 | 900 | 2025-05-08 | [7 empty] | 73 | 2025-07-20 |  | 0 | 0 | [7 empty] | 0
|  | Addanki | 58754 | 0 | 0 | 58754 | 700 | 1 | K2 | 700 | 2025-05-08 | [7 empty] | 89 | 2025-08-05 |  | 0 | 0 | [7 empty] | 0
|  | Markapuram | 33877 | 0 | 0 | 33877 | 700 | 1 | K3 | 700 | 2025-05-10 | [7 empty] | 71 | 2025-07-20 |  | 0 | 0 | [7 empty] | 0
|  | Chirala | 28392 | 0 | 0 | 28392 | 700 | 1 | K4 | 700 | 2025-05-10 | [7 empty] | 66 | 2025-07-15 |  | 0 | 0 | [7 empty] | 0
|  | Kandukuru | 26160 | 0 | 0 | 26160 | 700 | 1 | K5 | 700 | 2025-05-25 | [7 empty] | 36 | 2025-06-30 |  | 0 | 0 | [7 empty] | 0
|  | Chimakurthy | 14459 | 0 | 0 | 14459 |  |  | K1(M/C) | 900 | 2025-07-30 | [7 empty] | 20 | 2025-08-19 | K1(M/C) shifted to Chimakurty | 0 | 0 | [7 empty] | 0
|  | Kanigiri | 11662 | 0 | 0 | 11662 |  |  | K2(M/C) | 700 | 2025-06-30 | [7 empty] | 20 | 2025-07-20 | K2(M/C) shifted to Kanigiri | 0 | 0 | [7 empty] | 0
|  | Darsi | 1602 | 0 | 0 | 1602 | 0 |  | K3(S) | 700 | 2025-07-21 | [7 empty] | 3 | 2025-07-24 | Material Shifted to Markapuram | 0 | 0 | [7 empty] | 0
|  | Podili | 1075 | 0 | 0 | 1075 | 0 |  | K4(S) | 700 | 2025-07-16 | [7 empty] | 2 | 2025-07-18 | Material Shifted to Chirala | 0 | 0 | [7 empty] | 0
| Total |  | 237910 | 0 | 0 | 237910 | 3700 | [14 empty] | 0 | 0 | [7 empty] | 0
| Eluru, Cluster (11 ULBs) | Eluru | 53348 | 0 | 0 | 53348 | 960 | 2 | CM1 | 480 | 2025-05-21 | CM2 | 480 | 2025-05-21 |  |  |  |  | 85 | 2025-08-14 |  | 0 | 0 | [7 empty] | 0
|  | Gudivada | 42953 | 0 | 0 | 42953 | 480 | 1 | CM3 | 480 | 2025-05-21 | [7 empty] | 120 | 2025-09-18 |  | 0 | 0 | [7 empty] | 0
|  | Machilipatnam | 41861 | 0 | 0 | 41861 | 960 | 2 | CM4 | 480 | 2025-05-21 | CM5 | 480 | 2025-05-21 |  |  |  |  | 73 | 2025-08-02 |  | 0 | 0 | [7 empty] | 0
|  | Tadepalligudem | 30258 | 0 | 0 | 30258 | 600 | 600 | M22 | 600 | 2025-05-15 | [7 empty] | 138 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0
|  | Vijayawada | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0 | [7 empty] | 0
|  | Jaggaiahpet | 12987 | 0 | 0 | 12987 | 480 | 1 | CM6 | 480 | 2025-08-09 | [7 empty] | 37 | 2025-09-15 |  | 0 | 0 | [7 empty] | 0
|  | Kondapalli | 5000 | 0 | 0 | 5000 |  |  | CM4 (M/C) | 480 | 2025-08-22 | [7 empty] | 15 | 2025-09-06 |  | 0 | 0 | [7 empty] | 0
|  | Nandigama | 1398 | 0 | 0 | 1398 | 480 |  | CM5 | 480 | 2025-08-22 | [7 empty] | 6 | 2025-08-28 |  | 0 | 0 | [7 empty] | 0
|  | Nuzvid | 18458 | 0 | 0 | 18458 |  | 1 | CM6 (M/C) | 480 | 2025-05-21 | [7 empty] | 60 | 2025-07-20 |  | 0 | 0 | [7 empty] | 0
| Total |  | 206263 | 0 | 0 | 206263 | 3960 | [14 empty] | 0 | 0 | [7 empty] | 0
| Kadapa, Cluster (9 ULBs) | Proddatur | 70730 | 0 | 0 | 70730 | [15 empty] | 0 | 0 | [7 empty] | 0
|  | Rayachoti | 94604 | 0 | 0 | 94604 | [15 empty] | 0 | 0 | [7 empty] | 0
|  | Badvel | 11926 | 0 | 0 | 11926 | [15 empty] | 0 | 0 | [7 empty] | 0
|  | Rajampet | 11800 | 0 | 0 | 11800 |  | 600 | M24 | 600 | 2025-05-15 | [7 empty] | 65 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0
|  | Mydukur | 11244 | 0 | 0 | 11244 | [15 empty] | 0 | 0 | [7 empty] | 0
|  | Pulivendula | 10000 | 0 | 0 | 10000 | [15 empty] | 0 | 0 | [7 empty] | 0
|  | Jammalamadugu | 4916 | 0 | 0 | 4916 | [15 empty] | 0 | 0 | [7 empty] | 0
|  | Yerraguntla | 2021 | 0 | 0 | 2021 | [15 empty] | 0 | 0 | [7 empty] | 0
|  | Kamalapuram | 1763 | 0 | 0 | 1763 | [15 empty] | 0 | 0 | [7 empty] | 0
| Total |  | 219004 | 0 | 0 | 217241 | [15 empty] | 0 | 0 | [7 empty] | 0
| Total |  | 2173358.88 | 15104.61 | 14826.35 | 2156491.27 | 18160 | 8 | 0 | 3200 | 183130 | 0 | 3000 | 137409 | 0 | 2200 | 91570 | 0 | 590 | 183720 | 0 | 280.18 | 278.26 | [7 empty] | 278.26 | 0
| Cluster-1,2&3 | Yelamanchili | 8718.59 | 8718.59 | 8718.59 | 0 | [15 empty] | 0 | 0 | [7 empty] | 0
|  | Kovvur | 8775.13 | 8775.13 | 8775.13 | 0 | [15 empty] | 1 | 0 | [7 empty] | 0
|  | Amalapuram | 27910.22 | 27910.22 | 27910.22 | 0 | [15 empty] | 2 | 0 | [7 empty] | 0
|  | Nidadavole | 37207.27 | 37207.27 | 37207.27 | 0 | [15 empty] | 3 | 0 | [7 empty] | 0
|  | Pithapuram | 24910 | 24910 | 24910 | 0 | [15 empty] | 5 | 0 | [7 empty] | 0
|  | Peddapuram | 19612 | 19612 | 19612 | 0 | [15 empty] | 6 | 0 | [7 empty] | 0
|  | Rajam | 12829 | 12829 | 12829 | 0 | [15 empty] | 7 | 0 | [7 empty] | 0
|  | Tanuku | 74206 | 74206 | 74206 | 0 | [15 empty] | 8 | 0 | [7 empty] | 0
|  | Tuni | 22097.82 | 22097.82 | 22097.82 | 0 | [15 empty] | 9 | 0 | [7 empty] | 0
|  | Nuzvid | 15994.68 | 15994.68 | 15994.68 | 0 | [15 empty] | 10 | 0 | [7 empty] | 0
|  | Palacole | 25181 | 25181 | 25181 | 0 | [15 empty] | 11 | 0 | [7 empty] | 0
|  | Kondapalli | 4925 | 4925 | 4925 | 0 | [15 empty] | 12 | 0 | [7 empty] | 0
|  | YSR Tadigadapa | 50000 | 50000 | 50000 | 0 | [15 empty] | 13 | 0 | [7 empty] | 0
|  | Tiruvuru | 20842 | 20842 | 20842 | 0 | [15 empty] | 14 | 0 | [7 empty] | 0
|  | Samalkot | 37786 | 37786 | 37786 | 0 | [15 empty] | 15 | 0 | [7 empty] | 0
|  | Bobbili | 14711 | 11983 | 11983 | 2728 | [15 empty] | 16 | 0 | [7 empty] | 0 | Work on Hold dueto rain
|  | Gollaprolu NP | 13135 | 9476.81 | 9476.81 | 3658.19 | [15 empty] | 17 | 0 | [7 empty] | 0
|  | Ramachandrapuram | 22142.68 | 4255.74 | 4255.74 | 17886.94 | [15 empty] | 18 | 0 | [7 empty] | 0
|  | Narsapur | 51312 | 34887.4 | 34493 | 16424.6 | [15 empty] | 19 | 394.4 | [7 empty] | 394.4 | Work is in Progress
|  | Jangareddygudem | 18736 | 15601.44 | 15601.44 | 3134.56 | [15 empty] | 20 | 0 | [7 empty] | 0
|  | Mandapeta | 8779 | 0 | 0 | 8779 | [15 empty] | 21 | 0 | [7 empty] | 0
|  | Yeleswaram | 11022 | 0 | 0 | 11022 | [15 empty] | 22 | 0 | [7 empty] | 0
|  | Parvathipuram | 11921.09 | 0 | 0 | 11921.09 | [15 empty] | 23 | 0 | [7 empty] | 0
|  | Salur | 12042 | 0 | 0 | 12042 | [15 empty] | 24 | 0 | [7 empty] | 0
|  | Narsipatnam | 6250 | 0 | 0 | 6250 | [15 empty] | 25 | 0 | [7 empty] | 0
|  | Pedana | 5821 | 0 | 0 | 5821 | [15 empty] | 26 | 0 | [7 empty] | 0
|  | Chintalapudi | 7300 | 0 | 0 | 7300 | [15 empty] | 27 | 0 | [7 empty] | 0
|  | Vuyyuru | 10000 | 0 | 0 | 10000 | [15 empty] | 28 | 0 | [7 empty] | 0
| Total |  | 584166.48 | 467199.1 | 466804.7 | 116967.38 | [16 empty] | 394.4
| Totals |  | 2757525.36 | 482303.71 | 481631.05 | 2273458.65 | 18160 | 8 | 0 | 3200 | 183130 | 0 | 3000 | 137409 | 0 | 2200 | 91570 | 0 | 590 | 183720 |  |  | 672.66

## Coastline (ELURU Cluster)
Agency Wise Legacy Waste Status Abstract as on 25.05.2025 | Agency Wise Legacy Waste Details
Agency | Agency | Cluster | S.no | ULB | Quantity to be remediated in MT | Cumulative Quantity remediated till date in MT | Balance Quantity in MT | % of Comp. | Capacity of Machine per day to be installed (in MT) | No of Machines | Machine No | Daily capacity | Start date | No-of days requred for Completion | Expected date of completion | Quantity remediated on 12.05.2025 (in MT) | Quantity remediated on 13.05.2025 (in MT) | Quantity remediated on 14.05.2025 (in MT) | Quantity remediated on 15.05.2025 (in MT) | Quantity remediated on 16.05.2025 (in MT) | Quantity remediated on 21.05.2025 (in MT) | Quantity remediated on 17.05.2025 (in MT) | Quantity remediated on 18.05.2025 (in MT) | Quantity remediated on 19.05.2025 (in MT) | Quantity remediated on 20.05.2025 (in MT) | Difference B/W | Quantity remediated on 21.05.2025 (in MT) | Quantity remediated on 22.05.2025 (in MT) | Quantity remediated on 23.05.2025 (in MT) | Quantity remediated on 24.05.2025 (in MT) | Quantity remediated on 25.05.2025 (in MT) | Quantity remediated on 26.05.2025 (in MT) | Quantity remediated on 27.05.2025 (in MT) | Quantity remediated on 28.05.2025 (in MT) | Quantity remediated on 29.05.2025 (in MT) | Quantity remediated on 30.05.2025 (in MT) | Quantity remediated on 31.05.2025 (in MT) | Quantity remediated on 01.06.2025 (in MT) | Quantity remediated on 01.06.2025 (in MT) | Quantity remediated on 03.06.2025 (in MT) | Quantity remediated on 04.06.2025 (in MT) | Quantity remediated on 05.06.2025 (in MT) | Quantity remediated on 06.06.2025 (in MT) | Quantity remediated on 07.06.2025 (in MT) | Quantity remediated on 08.06.2025 (in MT) | Quantity remediated on 09.06.2025 (in MT) | Quantity remediated on 10.06.2025 (in MT) | Quantity remediated on 11.06.2025 (in MT) | Quantity remediated on 12.06.2025 (in MT) | Quantity remediated on 13.06.2025 (in MT) | Quantity remediated on 14.06.2025 (in MT) | Quantity remediated on 15.06.2025 (in MT) | Remarks | 30th April 2025 | 4th May 2025 | 5th May 2025 | 6th May 2025 | 7th May 2025 | 8th May 2025 | 1st May to 8th 2025 | Status
1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 10 | 11 | 12 | 13 | 14 | 16 | 16 | 16 | 16 | 17 | 17 | 16 | 16 | 16 | 16 | 18 | 16 | 16 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 17 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 16 | 15 | 16 | 17 | 21 | 24 | 25 |  | 26 | 27 | 28 | 20
| Tharuni Assosiates-Coastline | Eluru, Cluster | 1 | Eluru | 53348 | 2682 | 50666 | 5.027% | 960 | 2 | C-M1 | 960 | 2025-06-02 | 90 | 2025-09-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.37 | 346.79 | 179.76 | 0 | 0 | 0 | 86.21 | 0 | 237.93 | 0 | 276.83 | 313.44 | 449.84 | 558.91 | Work in progress | 0 | [5 empty] | 0
|  |  | 2 | Gudivada | 42953 | 0 | 42953 | 0% | 480 | 1 | C-M2 | 480 | 2025-06-20 | 97 | 2025-09-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Machine Fabrication work is progress at Machilipatnam site | 0 | [5 empty] | 0
|  |  | 3 | Machilipatnam | 41861 | 296 | 41565 | 0.7071% | 480 | 2 | C-M3 | 480 | 2025-06-13 | 86.5938 | 2025-08-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.5 | 176.84 | 101.17 | Work in progress | 0 | [5 empty] | 0
|  |  | 4 | Vijayawada | 0 | 0 | 0 | - | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0
|  |  | 5 | Jaggaiahpet | 12987 | 0 | 12987 | 0% | 480 |  | C-M4 |  | 2025-07-10 | 69 | 2025-09-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | New machine to be Installed | 0 | [5 empty] | 0
|  |  | 6 | Kondapalli | 5000 | 0 | 5000 | 0% |  |  | C-M4(S) |  | 2025-09-10 | 20 | 2025-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Kondapalli material 5000MT will be shifted to Jaggaiahpet | 0 | [5 empty] | 0
|  |  | 7 | Nandigama | 1398 | 0 | 1398 | 0% |  | 1 | C-M4(S) |  | 2025-09-10 | 10 | 2025-09-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Nandigama material 1398MT will be shifted to Jaggaiahpet | 0 | [5 empty] | 0
|  |  | 8 | Kovvur | 915 | 0 | 915 | 0% |  |  | M7 (S) |  | 2025-09-01 | 4 | 2025-09-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Kovvuru Material (915MT) Will be shifted to Rajahmundry
|  | Total |  |  | 158462 | 2978 | 155484 | 1.879% | 2400 | 6 | 4 | 1920 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.37 | 346.79 | 179.76 | 0 | 0 | 0 | 86.21 | 0 | 237.93 | 0 | 276.83 | 330.94 | 626.68 | 660.08 |  | 0 | [5 empty] | 0
4100

## (KADAPA Cluster)
Agency Wise Legacy Waste Status Abstract as on 25.05.2025 | Agency Wise Legacy Waste Details
Agency | Agency | Cluster | S.no | ULB | Quantity to be remediated in MT | Cumulative Quantity remediated till date in MT | Balance Quantity in MT | % of Comp. | Capacity of Machine per day to be installed (in MT) | No of Machines | Machine No | Daily capacity | Start date | No-of days requred for Completion | Expected date of completion | Quantity remediated on 12.05.2025 (in MT) | Quantity remediated on 13.05.2025 (in MT) | Quantity remediated on 14.05.2025 (in MT) | Quantity remediated on 15.05.2025 (in MT) | Quantity remediated on 16.05.2025 (in MT) | Quantity remediated on 21.05.2025 (in MT) | Quantity remediated on 17.05.2025 (in MT) | Quantity remediated on 18.05.2025 (in MT) | Quantity remediated on 19.05.2025 (in MT) | Quantity remediated on 20.05.2025 (in MT) | Quantity remediated on 21.05.2025 (in MT) | Difference B/W | Quantity remediated on 22.05.2025 (in MT) | Quantity remediated on 23.05.2025 (in MT) | Quantity remediated on 24.05.2025 (in MT) | Quantity remediated on 25.05.2025 (in MT) | Quantity remediated on 26.05.2025 (in MT) | Quantity remediated on 27.05.2025 (in MT) | Quantity remediated on 28.05.2025 (in MT) | Quantity remediated on 29.05.2025 (in MT) | Quantity remediated on 30.05.2025 (in MT) | Quantity remediated on 31.05.2025 (in MT) | Quantity remediated on 01.06.2025 (in MT) | Quantity remediated on 02.06.2025 (in MT) | Quantity remediated on 03.06.2025 (in MT) | Quantity remediated on 04.06.2025 (in MT) | Quantity remediated on 05.06.2025 (in MT) | Quantity remediated on 06.06.2025 (in MT) | Quantity remediated on 07.06.2025 (in MT) | Quantity remediated on 08.06.2025 (in MT) | Quantity remediated on 09.06.2025 (in MT) | Quantity remediated on 10.06.2025 (in MT) | Quantity remediated on 11.06.2025 (in MT) | Quantity remediated on 12.06.2025 (in MT) | Quantity remediated on 13.06.2025 (in MT) | Quantity remediated on 14.06.2025 (in MT) | Quantity remediated on 15.06.2025 (in MT) | Remarks | 30th April 2025 | 4th May 2025 | 5th May 2025 | 6th May 2025 | 7th May 2025 | 8th May 2025 | 1st May to 8th 2025 | Status
1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 16 | 16 | 16 | 17 | 17 | 16 | 16 | 16 | 16 | 16 | 20 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 17 | 15 | 15 | 16 | 16 | 15 | 15 | 15 | 15 | 15 | 16 | 16 | 15 | 16 | 17 | 21 | 24 | 25 |  | 26 | 27 | 28 | 20
| Tharuni Assosiates | Kadapa, Cluster (9 ULBs) | 1 | Proddatur | 70730 | 0 | 70730 | 0 | 1400 |  | M32 | 1400 | 2025-06-20 | 90 | 2025-09-30 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Machine Under Installation
[11 empty] | M31(M/C) |  | 2025-08-05 | 56 | 2025-09-30 | [37 empty] | M8(M/C)Will be Shifted from Mydkur
|  |  | 2 | Jammalamadugu | 4916 | 0 | 4916 | 0% |  |  | M32(S) |  | 2025-09-01 | 14 | 2025-09-14 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Jammalamadugu material4916MT will be shifted to proddatur
|  |  | 3 | Yerraguntla | 2021 | 0 | 2021 | 0% |  |  | M32(S) |  | 2025-09-15 | 15 | 2025-09-15 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yerraguntla Material 2021MT will be shifted to proddatur
|  |  | 4 | Rayachoti | 94604 | 0 | 94604 | 0 | 600 |  | M25 (M/C) | 600 | 2025-06-25 | 90 | 2025-09-30 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | M25(M/C) arried from Tuni
[9 empty] | 600 |  | M8 (M/C) |  | 2025-07-05 |  | 2025-08-30 | [37 empty] | M8(M/C) Will be Shifted from Gollapurolu
|  |  | 5 | Badvel (Hasper) | 11926 | 0 | 11926 | 0% | 500 | 1 | M29 | 500 | 2025-06-20 | 30 | 2025-07-10 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Machine Intsallation Completed. Weigh bridge yet to Installed
|  |  | 6 | Rajampet | 11800 | 0 | 11800 | 0% | 500 |  | M30 | 500 | 2025-06-25 | 30 | 2025-07-25 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | New machine Under Installation
|  |  | 7 | Mydukur | 11244 | 0 | 11244 | 0% | 1400 |  | M31 |  | 2025-07-01 | 30 | 2025-07-30 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | New machine to be Installed
|  |  | 8 | Pulivendula | 10000 | 0 | 10000 | 0% | [7 empty] | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No legacy available at site.
|  |  | 9 | Kamalapuram | 1763 | 0 | 1763 | 0% | 6 | 4100 | M3(S) |  | 2025-09-15 |  |  | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Kamalapuram material 1763MT shifted to kadapa
|  | Total |  |  | 219004 | 0 | 219004 | 0% | 5006 | 4101 | 4 | 3000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Srinivas (HINDUPUR Cluster)
Agency Wise Legacy Waste Status Abstract as on 25.05.2025 | Agency Wise Legacy Waste Details
Agency | Agency | Cluster | S.no | ULB | Quantity to be remediated in MT | Cumulative Quantity remediated till date in MT | Balance Quantity in MT | %of Comp. | Capacity of Machine per day to be installed (in MT) | No of Machines | Machine No | Daily capacity | Start date | No-of days requred for Completion | Expected date of completion | Quantity remediated on 12.05.2025 (in MT) | Quantity remediated on 13.05.2025 (in MT) | Quantity remediated on 14.05.2025 (in MT) | Quantity remediated on 15.05.2025 (in MT) | Quantity remediated on 16.05.2025 (in MT) | Quantity remediated on 21.05.2025 (in MT) | Quantity remediated on 17.05.2025 (in MT) | Difference B/W | Quantity remediated on 18.05.2025 (in MT) | Quantity remediated on 19.05.2025 (in MT) | Quantity remediated on 20.05.2025 (in MT) | Quantity remediated on 21.05.2025 (in MT) | Quantity remediated on 22.05.2025 (in MT) | Quantity remediated on 23.05.2025 (in MT) | Quantity remediated on 24.05.2025 (in MT) | Quantity remediated on 25.05.2025 (in MT) | Quantity remediated on 26.05.2025 (in MT) | Quantity remediated on 27.05.2025 (in MT) | Quantity remediated on 28.05.2025 (in MT) | Quantity remediated on 29.05.2025 (in MT) | Quantity remediated on 30.05.2025 (in MT) | Quantity remediated on 31.05.2025 (in MT) | Quantity remediated on 01.06.2025 (in MT) | Quantity remediated on 02.06.2025 (in MT) | Quantity remediated on 03.06.2025 (in MT) | Quantity remediated on 04.06.2025 (in MT) | Quantity remediated on 05.06.2025 (in MT) | Quantity remediated on 06.06.2025 (in MT) | Quantity remediated on 07.06.2025 (in MT) | Quantity remediated on 08.06.2025 (in MT) | Quantity remediated on 09.06.2025 (in MT) | Quantity remediated on 10.06.2025 (in MT) | Quantity remediated on 11.06.2025 (in MT) | Quantity remediated on 12.06.2025 (in MT) | Quantity remediated on 13.06.2025 (in MT) | Quantity remediated on 14.06.2025 (in MT) | Quantity remediated on 15.06.2025 (in MT) | Remarks | 30th April 2025 | 4th May 2025 | 5th May 2025 | 6th May 2025 | 7th May 2025 | 8th May 2025 | 1st May to 8th 2025 | Status
1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 10 | 11 | 12 | 13 | 14 | 16 | 16 | 16 | 16 | 17 | 17 | 16 | 21 | 16 | 16 | 16 | 16 | 16 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 15 | 15 | 16 | 17 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 16 | 15 | 16 | 17 | 21 | 24 | 25 |  | 26 | 27 | 28 | 20
| Tharuni Assosiates-Srinivas | Hindupur, Cluster (6 ULBs) | 1 | Hindupur | 49020 | 0 | 49020 | 0% | 700 | 1 | H-M1 | 700 | 2025-06-06 | 60 | 2025-08-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Machine has arrived near the site and currently waiting outside due to Political issue | 0 | [5 empty] | 0
|  | Hindupur, Cluster (6 ULBs) | 2 | Dharmavaram | 23000 | 463.66 | 22536.34 | 2.016% | 700 | 1 | H-M2 | 700 | 2025-06-10 | 50 | 2025-07-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121.7 | 167.23 | 174.73 | 0 | 0 | 0 | Data not recived from Tharuni associates | 0 | [5 empty] | 0
|  | Hindupur, Cluster (6 ULBs) | 3 | Kadiri | 20000 | 0 | 20000 | 0% |  |  | H-M2(S) |  | 2025-06-15 | 20 | 2025-07-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | Kadiri matrial 20000Mt Will be shifted to Dharmavaram | 0 | [5 empty] | 0
|  | Hindupur, Cluster (6 ULBs) | 4 | Penukonda | 13578 | 1346.33 | 12231.67 | 9.916% | 700 | 1 | H-M3 | 700 | 2025-06-10 | 25 | 2025-07-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300.01 | 285.71 | 760.52 | 0 | 0 | 0 | Data not recived from Tharuni associates | 0 | [5 empty] | 0
|  | Hindupur, Cluster (6 ULBs) | 5 | Madakasira | 664 | 664 | 0 | 100% |  |  | H-M3(S) |  | 2025-06-08 | 2 | 2025-06-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141.4 | 578 | 0 | 0 |  | 0 | 0 | 0 | Madakasira matrial 664Mt shifted Penukonda and Process also Completed
|  | Hindupur, Cluster (6 ULBs) | 6 | Puttaparthy | 10299 | 0 | 10299 | 0% |  |  | H-M3(S) |  | 2025-06-20 | 20 | 2025-07-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | Puttapaty matrial 10299Mt Will be shifted to Penukonda
|  | Total |  |  | 116561 | 2473.99 | 114087.01 | 2.122% | 2100 | 3 | 3 | 2100 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141.4 | 578 | 421.71 | 452.94 | 935.25 | 0 | 0 | 0 | [7 empty] | 0
4100

## Srinivas setty(ADDANKICluster)
Agency Wise Legacy Waste Status Abstract as on 25.05.2025 | Agency Wise Legacy Waste Details
Agency | Agency | Cluster | S.no | ULB | Quantity to be remediated in MT | Cumulative Quantity remediated till date in MT | Balance Quantity in MT | %of Comp. | Capacity of Machine per day to be installed (in MT) | No of Machines | Machine No | Daily capacity | Start date | No-of days requred for Completion | Expected date of completion | Quantity remediated on 14.05.2025 (in MT) | Quantity remediated on 15.05.2025 (in MT) | Quantity remediated on 16.05.2025 (in MT) | Quantity remediated on 13.05.2025 (in MT) | Quantity remediated on 12.05.2025 (in MT) | Quantity remediated on 21.05.2025 (in MT) | Difference B/W | Quantity remediated on 17.05.2025 (in MT) | Quantity remediated on 18.05.2025 (in MT) | Quantity remediated on 19.05.2025 (in MT) | Quantity remediated on 20.05.2025 (in MT) | Quantity remediated on 21.05.2025 (in MT) | Quantity remediated on 22.05.2025 (in MT) | Quantity remediated on 23.05.2025 (in MT) | Quantity remediated on 24.05.2025 (in MT) | Quantity remediated on 25.05.2025 (in MT) | Quantity remediated on 26.05.2025 (in MT) | Quantity remediated on 27.05.2025 (in MT) | Quantity remediated on 28.05.2025 (in MT) | Quantity remediated on 29.05.2025 (in MT) | Quantity remediated on 30.05.2025 (in MT) | Quantity remediated on 31.05.2025 (in MT) | Quantity remediated on 01.06.2025 (in MT) | Quantity remediated on 02.06.2025 (in MT) | Quantity remediated on 03.06.2025 (in MT) | Quantity remediated on 04.06.2025 (in MT) | Quantity remediated on 05.06.2025 (in MT) | Quantity remediated on 06.06.2025 (in MT) | Quantity remediated on 07.06.2025 (in MT) | Quantity remediated on 08.06.2025 (in MT) | Quantity remediated on 09.06.2025 (in MT) | Quantity remediated on 10.06.2025 (in MT) | Quantity remediated on 11.06.2025 (in MT) | Quantity remediated on 12.06.2025 (in MT) | Quantity remediated on 13.06.2025 (in MT) | Quantity remediated on 14.06.2025 (in MT) | Quantity remediated on 15.06.2025 (in MT) | Remarks | 30th April 2025 | 4th May 2025 | 5th May 2025 | 6th May 2025 | 7th May 2025 | 8th May 2025 | 1st May to 8th 2025 | Status
1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 10 | 11 | 12 | 13 | 14 | 16 | 16 | 17 | 16 | 16 | 16 | 17 | 16 | 16 | 16 | 16 | 16 | 16 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 17 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 16 |  | 15 | 16 | 17 | 21 | 24 | 25 |  | 26 | 27 | 28 | 20
| Tharuni Assosiates-Srinivas setty | Addanki, Cluster (9 ULBs) | 1 | Ongole | 61929 | 9159 | 52770 | 14.79% | 900 | 1 | A-M1 | 900 | 2025-05-28 | 53 | 2025-07-20 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244.46 | 339.99 | 406.04 | 631.72 | 584 | 235.77 | 905.74 | 746.5 | 286.03 | 719.73 | 727.71 | 203.33 | 394.73 | 210.15 | 418.33 | 497.98 | 439.67 | 753.95 | 412.42 | Work in progress | 0 | [5 empty] | 0
|  | Addanki, Cluster (9 ULBs) | 2 | Addanki | 58754 | 2000 | 56754 | 3.404% | 700 | 1 | A-M2 | 700 | 2025-06-10 | 56 | 2025-08-05 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 600 | 600 | 400 | 400 | 1.Work in progress 2.The value is taken appaoximately due to Printer Issue | 0 | [5 empty] | 0
|  | Addanki, Cluster (9 ULBs) | 3 | Markapuram | 33877 | 0 | 33877 | 0% | 700 | 1 | A-M3 | 700 | 2025-06-20 | 48.3957 | 2025-07-30 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Machine Installatiobn Completed.Waiting for Inaugaration | 0 | [5 empty] | 0
|  | Addanki, Cluster (9 ULBs) | 4 | Chirala | 28392 | 0 | 28392 | 0% |  | 1 | A-M4 |  | 2025-08-15 | 40.56 | 2025-09-30 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | New machine to be Deployed | 0 | [5 empty] | 0
|  | Addanki, Cluster (9 ULBs) | 5 | Kandukuru | 26160 | 0 | 26160 | 0% | 700 | 1 | A-M5 |  | 2025-06-20 | 40 | 2025-07-30 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | New machine to be Deployed | 0 | [5 empty] | 0
|  | Addanki, Cluster (9 ULBs) | 6 | Chimakurthy | 14459 | 0 | 14459 | 0% |  |  | A-M6 |  | 2025-07-30 | 20 | 2025-08-19 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | New machine to be Deployed to achive the target quantity. | 0 | [5 empty] | 0
|  | Addanki, Cluster (9 ULBs) | 7 | Kanigiri | 11662 | 0 | 11662 | 0% |  |  | A-M3(M/C) |  | 2025-06-30 | 20 | 2025-07-20 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A-M2(M/C) shifted from Markapuram | 0 | [5 empty] | 0
|  | Addanki, Cluster (9 ULBs) | 8 | Darsi | 1602 | 0 | 1602 | 0% | 0 |  | A-M3(S) |  | 2025-07-21 | 3 | 2025-07-24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Darsi material1602MT will beShifted to Kanigiri | 0 | [5 empty] | 0
|  | Addanki, Cluster (9 ULBs) | 9 | Podili | 1075 | 0 | 1075 | 0% | 0 |  | A-M4(S) |  | 2025-07-16 | 2 | 2025-07-18 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Podili material1075MT will be Shifted to Kanigiri | 0 | [5 empty] | 0
|  | Total |  |  | 237910 | 11159 | 226751 | 4.69% | 3000 | 5 | 5 | 2300 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244.46 | 339.99 | 406.04 | 631.72 | 584 | 235.77 | 905.74 | 746.5 | 286.03 | 719.73 | 727.71 | 203.33 | 394.73 | 210.15 | 818.33 | 1097.98 | 1039.67 | 1153.95 | 812.42 |  | 0 | [5 empty] | 0
[9 empty] | 6 | 4100

## V.Raju
Agency Wise Legacy Waste Status Abstract as on 25.05.2025 | Agency Wise Legacy Waste Details
Agency | Agency | Cluster | S.no | ULB | Quantity to be remediated in MT | Cumulative Quantity remediated till date in MT | Balance Quantity in MT | % of Comp. | Capacity of Machine per day to be installed (in MT) | No of Machines | Machine No | Daily capacity | Start date | No-of days requred for Completion | Expected date of completion | Quantity remediated on 12.05.2025 (in MT) | Quantity remediated on 13.05.2025 (in MT) | Quantity remediated on 14.05.2025 (in MT) | Quantity remediated on 15.05.2025 (in MT) | Quantity remediated on 16.05.2025 (in MT) | Quantity remediated on 21.05.2025 (in MT) | Quantity remediated on 17.05.2025 (in MT) | Quantity remediated on 18.05.2025 (in MT) | Quantity remediated on 19.05.2025 (in MT) | Quantity remediated on 20.05.2025 (in MT) | Difference B/W | Quantity remediated on 21.05.2025 (in MT) | Quantity remediated on 22.05.2025 (in MT) | Quantity remediated on 23.05.2025 (in MT) | Quantity remediated on 24.05.2025 (in MT) | Quantity remediated on 25.05.2025 (in MT) | Quantity remediated on 26.05.2025 (in MT) | Quantity remediated on 27.05.2025 (in MT) | Quantity remediated on 28.05.2025 (in MT) | Quantity remediated on 29.05.2025 (in MT) | Quantity remediated on 30.05.2025 (in MT) | Quantity remediated on 31.05.2025 (in MT) | Quantity remediated on 01.06.2025 (in MT) | Quantity remediated on 02.06.2025 (in MT) | Quantity remediated on 03.06.2025 (in MT) | Quantity remediated on 04.06.2025 (in MT) | Quantity remediated on 05.06.2025 (in MT) | Quantity remediated on 06.06.2025 (in MT) | Quantity remediated on 07.06.2025 (in MT) | Quantity remediated on 08.06.2025 (in MT) | Quantity remediated on 09.06.2025 (in MT) | Quantity remediated on 10.06.2025 (in MT) | Quantity remediated on 11.06.2025 (in MT) | Quantity remediated on 12.06.2025 (in MT) | Quantity remediated on 13.06.2025 (in MT) | Quantity remediated on 14.06.2025 (in MT) | Quantity remediated on 15.06.2025 (in MT) | Remarks | 30th April 2025 | 4th May 2025 | 5th May 2025 | 6th May 2025 | 7th May 2025 | 8th May 2025 | 1st May to 8th 2025 | Status
1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 10 | 11 | 12 | 123 | 14 | 16 | 16 | 16 | 16 | 17 | 17 | 16 | 16 | 16 | 16 | 18 | 16 | 16 | 15 | 15 | 15 | 15 | 15 | 16 | 15 | 15 | 15 | 16 | 17 | 15 | 15 | 15 | 15 | 16 | 15 | 15 | 15 | 15 | 16 |  | 15 | 16 | 17 | 21 | 24 | 25 |  | 26 | 27 | 28 | 20
| Tharuni Assosiates- V.Raju | Eluru, Cluster | 1 | Bhimavaram | 32358 | 0 | 32358 | 0% | 1000 | 2 | M20 | 500 | 2025-06-15 | 107 | 2025-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | p | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Ready to start. Awaiting for Inaugaration | 0 | [5 empty] | 0
[11 empty] | M21 |  | 2025-07-01 |  | 2025-09-30 | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 2 | Tadepalli-gudem | 30258 | 0 | 30258 | 0% | 500 |  | M22 |  | 2025-06-30 |  | 2025-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Local residence restraining | 0 | [5 empty] | 0
|  |  | 3 | Nuzvid | 18458 | 0 | 18458 | 0% | 400 | 1 | M23 | 400 | 2025-06-26 | 45 | 2025-08-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Machine and Weigh bridge Under Installation
|  | Kakinada, | 4 | Palacole | 30000 | 317 | 29683 | 1.057% | 600 | 1 | M19 | 600 | 2025-06-10 | 55 | 2025-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 317 | Work in progrss | 0 |  |  | Machinery under installation
|  | Total |  |  | 111074 | 317 | 110757 | 0.2854% | 2500 | 4 | 5 | 1500 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 317 |  | 0 | [5 empty] | 0
4100

## Zigma
Agency Wise Legacy Waste Details
Agency Name | Cluster | S.No. | Name of the ULB | Quantity to be remediated in MT | Cumulative Quantity remediated till date in MT | Balance Quantity in MT | % of Comp. | Capacity of Machine per day to be installed (in MT) | No of Machines | Details of Machinery |  |  |  |  | Quantity remediated on 14.05.2025 (in MT) | Quantity remediated on 15.05.2025 (in MT) | Quantity remediated on 16.05.2025 (in MT) | Quantity remediated on 13.05.2025 (in MT) | Quantity remediated on 12.05.2025 (in MT) | Difference b/w Col.11 & Col.15 | Quantity remediated on 21.05.2025 (in MT) | Quantity remediated on 17.05.2025 (in MT) | Quantity remediated on 18.05.2025 (in MT) | Quantity remediated on 19.05.2025 (in MT) | Quantity remediated on 20.05.2025 (in MT) | Quantity remediated on 21.05.2025 (in MT) | Quantity remediated on 22.05.2025 (in MT) | Quantity remediated on 23.05.2025 (in MT) | Quantity remediated on 24.05.2025 (in MT) | Quantity remediated on 25.05.2025 (in MT) | Quantity remediated on 26.05.2025 (in MT) | Quantity remediated on 27.05.2025 (in MT) | Quantity remediated on 28.05.2025 (in MT) | Quantity remediated on 29.05.2025 (in MT) | Quantity remediated on 30.05.2025 (in MT) | Quantity remediated on 31.05.2025 (in MT) | Quantity remediated on 01.06.2025 (in MT) | Quantity remediated on 02.06.2025 (in MT) | Quantity remediated on 03.06.2025 (in MT) | Quantity remediated on 04.06.2025 (in MT) | Quantity remediated on 05.06.2025 (in MT) | Quantity remediated on 06.06.2025 (in MT) | Quantity remediated on 07.06.2025 (in MT) | Quantity remediated on 08.06.2025 (in MT) | Quantity remediated on 09.06.2025 (in MT) | Quantity remediated on 10.06.2025 (in MT) | Quantity remediated on 11.06.2025 (in MT) | Quantity remediated on 12.06.2025 (in MT) | Quantity remediated on 13.06.2025 (in MT) | Quantity remediated on 14.06.2025 (in MT) | Quantity remediated on 15.06.2025 (in MT) | Remarks
[10 empty] | No. Machines | Daily capacity | Starting date | No. of days | Expected date of Completion Date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 20 | 16 | 16 | 16 | 16 | 16 | 16 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 17 | 15 | 15 | 15 | 15 | 16 | 15 | 15 | 15 | 15 | 16 |  | 15 | 16 | 17
M/s Zigma global Enviro Solutions Private limited, Erode | Nellore Municipal Corporation | 1 | Allipuram | 34037 | 31432 | 2605 | 92.35% | 800 | 1 | M2 | 800 | 2025-04-19 | 67 | 2025-06-25 | 795.67 | 223.93 | 447.97 | 709.64 | 703.96 |  |  | 784.95 | 736.83 | 0 | 0 | 115 | 0 | 0 | 295.25 | 0 | 430.19 | 759.14 | 841.38 | 752.97 | 162.9 | 284.86 | 849.08 | 661.65 | 837.02 | 305.41 | 744 | 600.04 | 629.29 | 1067.41 | 876.11 | 956.8 | 759.98 | 881.42 | 563.13 | 894.85 | 398.63 | Work in progress
|  |  | Donthali | 290442 | 8567 | 281875 | 2.95% | 1400 | 2 | M4 | 600 | 2025-05-25 | 109 | 2025-09-11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 431.21 | 0 | 395.34 | 0 | 0 | 0 | 496.91 | 343.52 | 330.29 | 616.84 | 649.11 | 721.73 | 540.89 | 0 | 452.77 | 463.24 | 349.29 | 612.03 | 428.58 | 441.84 | 569.98 | 723.33 | Work in progress
[10 empty] | M15 | 800 | [40 empty] | M15 erection under progress
|  |  |  | 324479 | 39999 | 284480 | 12.33% | 2200 | 3 | 3 | 2200 |  | 0 |  | 795.67 | 223.93 | 447.97 | 709.64 | 703.96 |  |  | 784.95 | 736.83 | 0 | 0 | 115 | 0 | 0 | 295.25 | 431.21 | 430.19 | 1154.48 | 841.38 | 752.97 | 162.9 | 781.77 | 1192.6 | 991.94 | 1453.86 | 954.52 | 1465.73 | 1140.93 | 629.29 | 1520.18 | 1339.35 | 1306.09 | 1372.01 | 1310 | 1004.97 | 1464.83 | 1121.96
M/s Zigma global Enviro Solutions Private limited, Erode | Nellore, Cluster (6 ULBs) | 2 | Alluru | 908 | 0 | 908 | 0% |  |  | M4(S) |  | 2025-07-06 | 2 | 2025-07-08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Alluru material 908MT will be shifted to Nellore
|  | 3 | Buchireddy-palem | 6030 | 0 | 6030 | 0% |  |  | M4(S) |  | 2025-06-22 | 15 | 2025-07-07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Buchireddipalem material 6030 MT will be shifted to Nellore
|  | 4 | Kavali | 18536 | 0 | 18536 | 0% | 400 |  | M16 |  | 2025-06-20 | 56 | 2025-08-15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pre segregation work in Progress
|  | 5 | Gudur(N) | 26563 | 0 | 26563 | 0% | 400 |  | M19 |  | 2025-06-30 | 66 | 2025-09-04 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | New machine to be deployed
|  | 6 | Naidupet | 4186 | 0 | 4186 | 0% |  |  | M19 (S) |  | 2025-09-04 | 10 | 2025-09-14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Naidupet material 4186MT will be shifted to Gudur(N)
|  | 7 | Atmakur(N) | 12784 | 0 | 12784 | 0% | 500 |  | M14 | 500 | 2025-06-15 | 25 | 2025-07-10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Machine Under Installation
|  |  |  | 62069 | 0 | 62069 | 0% | 1300 |  | 3 | 500 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
M/s Zigma global | GVMC | 8 | GVMC | 201400 | 136856 | 64544 | 67.95% | 1300 | 1 | M1 | 1300 | 2025-03-10 | 154 | 2025-08-11 | 1529 | 946.13 | 1634.37 | 1585.99 | 1113 |  |  | 1835.86 | 1535.3 | 1066.15 | 383.93 | 1038.1 | 1598.09 | 1766.58 | 1688.39 | 1386.18 | 1638.8 | 1449.66 | 0 | 910.6 | 1113.74 | 89.77 | 1379 | 1537.87 | 2187.82 | 1207.2 | 1505.16 | 1399.76 | 1442.92 | 1736.09 | 1505.16 | 753.46 | 1107.93 | 412.56 | 1578.52 | 1730.5 | 1713.16 | Work in progress
M/s Zigma global Enviro Solutions Private limited, Erode | Chittoor, Cluster (6 ULBs) | 9 | Chittoor | 146232 |  | 146232 | 0% | 1000 | 1 | M9 | 1000 | 2025-06-19 | 88 | 2025-09-15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. Machine Under Installation. 2. As per agency, date has been changed from 10.06.2025 to 19.06.2025. 3.Fresh Waste is dumping at Site.
[10 empty] | M7 M/c |  | 2025-07-25 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | M7 (M/C) Shifted to Chittoor from Palamaneru on 25-07-2025
|  | 10 | Madanapalle | 27532 | 8246 | 19286 | 29.95% | 500 | 1 | M3 | 500 | 2025-05-21 | 55 | 2025-07-15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 43 | 335 | 275.64 | 468.05 | 410 | 0 | 407.05 | 309.88 | 313.57 | 398.32 | 252.59 | 0 | 0 | 57.7 | 336.31 | 409.84 | 409.84 | 486.47 | 646.31 | 730.06 | 523.28 | 183.5 | 402.48 | 0 | 0 | 514.17 | Work in progress
|  | 11 | Punganur | 22945 | 3230 | 19715 | 14.08% | 500 | 1 | M8 | 500 | 2025-06-08 | 40 | 2025-07-18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316.695 | 373.68 | 177.77 | 433.515 | 569.21 | 438.12 | 470.02 | 628.39 | Work in progress
|  | 12 | B.Kothakota | 25772 | 0 | 25772 | 0% |  |  | M4(S) |  | 2025-07-16 | 51 | 2025-09-05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | B.Kothakota material 25772Mt will be shifted to Punganur
|  | 13 | Kuppam | 20000 | 5522 | 14478 | 27.61% | 500 | 6 | M16 | 500 | 2025-05-31 | 40 | 2025-07-10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 212 | 231.13 | 205.68 | 131.62 | 497.14 | 497.14 | 663.47 | 425.5 | 326.74 | 46.18 | 668.12 | 429.89 | 318.8 | 461.25 | 460.12 | Work in Progress
|  | 14 | Palamaneru | 13177 | 3327 | 9850 | 25.25% | 500 | 1 | M7 | 500 | 2025-05-31 | 45 | 2025-07-15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.75 | 13.69 | 18.96 | 0 | 0 | 286.77 | 0 | 0 | 0 | 0 | 259.05 | 391.055 | 837.05 | 502.205 | 558.945 | 455.32 | Work in Progress
|  |  |  | 255658 | 20325 | 235333 | 7.95% | 3000 |  | 6 | 3000 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 43 | 335 | 275.64 | 468.05 | 410 | 0 | 407.05 | 309.88 | 313.57 | 398.32 | 431.34 | 225.69 | 250.09 | 263.38 | 467.93 | 1193.75 | 906.98 | 1149.94 | 1388.505 | 1430.48 | 1006.28 | 1676.19 | 2238.63
M/s Zigma global Enviro Solutions Private limited, Erode | Tirupati, Cluster (6 ULBs) | 15 | Tirupati | 221473 | 6098 | 215375 | 2.753% | 2600 | 1 | M6 | 800 | 2025-05-31 | 85 | 2025-08-24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137 | 0 | 0 | 9.85 | 429.96 | 0 | 726.27 | 92.7 | 671.84 | 299.46 | 90.15 | 774.56 | 840.36 | 531.89 | 587.47 | 906.63 | Work in progress
[10 empty] | M18A | 800 | [37 empty] | 0 | 0 | 0 | New machine to be deployed of 800MT
[10 empty] | M18B | 1000 | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | New machine to be deployed of 1000MT
|  | 16 | Srikalahasti | 50307 | 0 | 50307 | 0% | 800 | 1 | M10 | 800 | 2025-06-13 | 59 | 2025-08-11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Machine Installation Completeed.Weigh bridge Calibration pending
|  | 17 | Sullurpet | 38261 | 0 | 38261 | 0% | 800 | 1 | M11 | 800 | 2025-06-15 | 42 | 2025-07-27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Machine and Weigh bridge Under Installation
|  | 18 | Puttur | 20034 | 0 | 20034 | 0% | 400 |  | M12 | 400 | 2025-06-16 | 44 | 2025-07-30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Machine Under Installation
|  | 19 | Nagari | 21977 | 0 | 21977 | 0% |  |  | M4 (M/C)(S) |  | 2025-07-30 | 50 | 2025-09-18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 20 | Venkatagiri | 15093 | 0 | 15093 | 0% | 500 | 1 | M13 | 500 | 2025-06-16 | 24 | 2025-07-10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 367145 | 6098 | 361047 | 1.661% | 5100 |  | 6 | 5100 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137 | 0 | 0 | 9.85 | 429.96 | 0 | 726.27 | 92.7 | 671.84 | 299.46 | 90.15 | 774.56 | 840.36 | 531.89 | 587.47 | 906.63 | 0 | 0
M/s Zigma global Enviro Solutions Private limited, Erode | Anantapur, Cluster (6 ULBs) | 21 | Anantapur | 168285 | 0 | 168285 | 0% | 1800 |  | M17 +M20 |  | 2025-06-18 | 93 | 2025-09-19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
|  | 22 | Tadipatri | 22735 | 0 | 22735 | 0% |  |  | M8(M/C) |  | 2025-07-10 | 45 | 2025-08-24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
|  | 23 | Guntakal | 20000 | 0 | 20000 | 0% |  |  | M9(M/C) |  | 2025-07-18 | 40 | 2025-08-27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
|  | 24 | Gooty | 4563 | 0 | 4563 | 0% |  |  | M9(S) |  | 2025-08-27 | 10 | 2025-09-06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Qty Shifted to Guntakal
|  | 25 | Kalyanadurgam | 7184 | 0 | 7184 | 0% | 400 |  | M21 |  | 2025-07-27 | 17 | 2025-08-13 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | New Machine Orderd M21
|  | 26 | Rayadurgam | 6919 | 0 | 6919 | 0% |  |  | M21(M/C) |  | 2025-08-28 | 18 | 2025-09-15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | M21(M/C) Shifted to Kalyanadurgam
|  |  |  | 229686 | 0 | 229686 | 0% | 2200 |  | 3 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 1440437 | 203278 | 1237159 | 14.11% | 15100 |  | 21 | 12100 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 4930.69 | 4801.55 | 3115.38 | 3782.8 | 3741.75
[13 empty] | 2025-05-25 |  |  |  |  | 2025-06-15
[13 empty] | 2025-05-15 |  |  |  |  | 2025-06-14

## Saurastra
Agency Wise Legacy Waste Details
Agency | Agency Name | Cluster | S. No. | ULB | Quantity to be remediated in MT | Cumulative Quantity remediated till date in MT | Balance Quantity in MT | % of Comp. | Capacity of Machine per day to be installed (in MT) | No of Machines | Details of Machinery |  |  |  |  | Quantity remediated on 14.05.2025 (in MT) | Quantity remediated on 15.05.2025 (in MT) | Quantity remediated on 16.05.2025 (in MT) | Quantity remediated on 13.05.2025 (in MT) | Quantity remediated on 12.05.2025 (in MT) | Quantity remediated on 21.05.2025 (in MT) | Difference b/n Col.11 & Col.15 | Quantity remediated on 17.05.2025 (in MT) | Quantity remediated on 18.05.2025 (in MT) | Quantity remediated on 19.05.2025 (in MT) | Quantity remediated on 20.05.2025 (in MT) | Quantity remediated on 21.05.2025 (in MT) | Quantity remediated on 22.05.2025 (in MT) | Quantity remediated on 23.05.2025 (in MT) | Quantity remediated on 24.05.2025 (in MT) | Quantity remediated on 25.05.2025 (in MT) | Quantity remediated on 26.05.2025 (in MT) | Quantity remediated on 27.05.2025 (in MT) | Quantity remediated on 28.05.2025 (in MT) | Quantity remediated on 29.05.2025 (in MT) | Quantity remediated on 30.05.2025 (in MT) | Quantity remediated on 31.05.2025 (in MT) | Quantity remediated on 01.06.2025 (in MT) | Quantity remediated on 02.06.2025 (in MT) | Quantity remediated on 03.06.2025 (in MT) | Quantity remediated on 04.06.2025 (in MT) | Quantity remediated on 05.06.2025 (in MT) | Quantity remediated on 06.06.2025 (in MT) | Quantity remediated on 07.06.2025 (in MT) | Quantity remediated on 08.06.2025 (in MT) | Quantity remediated on 09.06.2025 (in MT) | Quantity remediated on 10.06.2025 (in MT) | Quantity remediated on 11.06.2025 (in MT) | Quantity remediated on 12.06.2025 (in MT) | Quantity remediated on 13.06.2025 (in MT) | Quantity remediated on 14.06.2025 (in MT) | Quantity remediated on 15.06.2025 (in MT) | Remarks
[11 empty] | No. Machines | Daily capacity | Start date | No. of days | Completion Date
1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 10 | 11 | 12 | 13 | 14 | 16 | 16 | 17 | 19 | 20 | 20 | 21 | 16 | 16 | 16 | 16 | 16 | 16 | 15 | 15 | 16 | 15 | 15 | 16 | 15 | 16 | 15 | 16 | 17 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 15 | 15 | 16 | 17
M/s Saurastra Enviro Pvt Ltd, Gujarat | M/s Saurastra Enviro Pvt Ltd, Gujarat | Kurnool, Cluster (5 ULBs) | 1 | Kurnool | 67308 | 49401 | 17907 | 73.4% | 1800 | 1 | M1 | 1800 | 29.04.2025 | 45 | 30.06.2025 | 715.115 | 984.47 | 1412.64 | 1055.11 | 974.22 | 974.22 |  | 1540.41 | 0 | 1862.2 | 1756 | 1453.225 | 1113.945 | 1785.35 | 1370.995 | 1148.855 | 557.05 | 1683.115 | 1398.3 | 1431.02 | 1511.2 | 2196.91 | 1400.08 | 1143.25 | 0 | 1136.62 | 1205.005 | 856.15 | 878.84 | 874.57 | 803.995 | 1059.37 | 625.99 | 606.77 | 1197.12 | 795.49 | 176.3 | Work is in Progress
|  |  | 2 | Gudur(K) | 2666 | 0 | 2666 | 0% |  |  | M1(S) |  | 15.06.2025 | 5 | 20.06.2025 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Quantity 2666MT will be shifted to Kurnool
|  |  | 3 | Dhone | 50000 | 0 | 50000 | 0% | 1200 | 1 | M2 |  | 18.06.2025 | 42 | 30.07.2025 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Machine Will be arrived on 12-06-2025
|  |  | 4 | Yemmi-ganur | 41357 | 3477 | 37880 | 8.407% | 600 | 1 | M3 | 600 | 02.06.2025 | 75 | 30.07.2025 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 505.66 |  | 0 | 572.57 | 466.61 | 157.7 | 0 | 0 | 0 | 0 | 0 | 0 | 176.03 | 746.45 | Work in progress
|  |  | 5 | Adoni | 10000 | 0 | 10000 | 0% |  |  | M2 (M/c) |  | 10.08.2025 | 10 | 20.08.2025 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | M2 M/c will be shifted from Dhone
[5 empty] | 171331 | 52878 | 118453 | 30.86% | 3600 | 3 | 3 | 2400 |  |  |  | 715.115 | 984.47 | 1412.64 | 1055.11 | 974.22 | 974.22 |  | 1540.41 | 0 | 1862.2 | 1756 | 1453.225 | 1113.945 | 1785.35 | 1370.995 | 1148.855 | 557.05 | 1683.115 | 1398.3 | 1431.02 | 1511.2 | 2196.91 | 1400.08 | 1648.91 | 0 | 1136.62 | 1777.575 | 1322.76 | 1036.54 | 874.57 | 803.995 | 1059.37 | 625.99 | 606.77 | 1197.12 | 971.52 | 922.75
| M/s Saurastra Enviro Pvt Ltd, Gujarat | Nandyal, Cluster (6 ULBs) | 6 | Nandyal | 80083 | 42510 | 37573 | 53.08% | 1800 | 1 | M4 | 1800 | 28.04.2025 | 50 | 30.06.2025 | 1130.13 | 667.92 | 1309.76 | 1197.08 | 668.01 | 668.01 |  | 980.76 | 740.04 | 1306.38 | 1240.92 | 950.13 | 632.39 | 824.25 | 951.57 | 1319.66 | 684.73 | 455.49 | 1764.13 | 687.18 | 1315 | 1858.68 | 1473.45 | 1205.33 | 873.09 | 989.56 | 1741.26 | 1741.26 | 1447.53 | 848.98 | 246.77 | 968.62 | 809.51 | 0 | 0 | 0 | 491.42 | Work in Progress
|  |  | 7 | Betham-cherla | 24189 | 0 | 24189 | 0% | 1200 | 1 | M5 | 1200 | 15.06.2025 | 30 | 15.07.2025 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Machine Installation and Weigh bridge Work In progress
|  |  | 8 | Nandikotkur | 19700 | 0 | 19700 | 0% |  |  | M5 (M/c) |  | 25.07.2025 | 20 | 15.08.2025 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | M5 M/c will be shifted from Bethamcherla
|  |  | 9 | Atmakur (K) | 3596 | 0 | 3596 | 0% |  |  | M5 (S) |  | 06.07.2025 | 5 | 10.07.2025 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Quantity 3596MT will be shifted to Nandikotkur
|  |  | 10 | Giddalur | 9773 | 0 | 9773 | 0% | 6 | 4100 | M6 |  | 30.06.2025 | 20 | 20.07.2025 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 11 | Allagadda | 6153 | 0 | 6153 | 0% |  |  | M6 (M/c) |  | 30.07.2025 | 15 | 15.08.2025 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | M6 M/c shifted from Giddalur
[5 empty] | 143494 | 42510 | 100984 | 29.62% | 3006 | 4102 | 3 | 3000 |  |  |  | 1130.13 | 667.92 | 1309.76 | 1197.08 | 668.01 | 668.01 |  | 980.76 | 740.04 | 1306.38 | 1240.92 | 950.13 | 632.39 | 824.25 | 951.57 | 1319.66 | 684.73 | 455.49 | 1764.13 | 687.18 | 1315 | 1858.68 | 1473.45 | 1205.33 | 873.09 | 989.56 | 1741.26 | 1741.26 | 1447.53 | 848.98 | 246.77 | 968.62 | 809.51 | 0 | 0 | 0 | 491.42
|  |  |  | Total | 314825 | 95388 | 219437 | 30.3% | 6606 | 4105 | 6 | 5400 |  |  |  | 1845.245 | 1652.39 | 2722.4 | 2252.19 | 1642.23 | 1642.23 |  | 2521.17 | 740.04 | 3168.58 | 2996.92 | 2403.355 | 1746.335 | 2609.6 | 2322.565 | 2468.515 | 1241.78 | 2138.605 | 3162.43 | 2118.2 | 2826.2 | 4055.59 | 2873.53 | 2854.24 | 873.09 | 2126.18 | 3518.835 | 3064.02 | 2484.07 | 1723.55 | 1050.765 | 2027.99 | 1435.5 | 606.77 | 1197.12 | 971.52 | 1414.17
[14 empty] | 2025-05-25 |  |  |  |  | 2025-06-15
[14 empty] | 2025-05-15 |  |  |  |  | 2025-06-14

## Tharuni Associates Old Cluster
Agency Wise Legacy Waste Status Abstract as on 25.05.2025 | Agency Wise Legacy Waste Details
Agency | Agency | Cluster | S.no | ULB | Quantity to be remediated in MT | Cumulative Quantity remediated till date in MT | Balance Quantity in MT | % of Comp. | Capacity of Machine per day to be installed (in MT) | No of Machines | Machine No | Daily capacity | Start date | No-of days requred for Completion | Expected date of completion | Quantity remediated on 14.05.2025 (in MT) | Quantity remediated on 15.05.2025 (in MT) | Quantity remediated on 16.05.2025 (in MT) | Quantity remediated on 13.05.2025 (in MT) | Quantity remediated on 13.05.2025 (in MT) | Quantity remediated on 21.05.2025 (in MT) | Quantity remediated on 12.05.2025 (in MT) | Difference B/W | Quantity remediated on 17.05.2025 (in MT) | Quantity remediated on 18.05.2025 (in MT) | Quantity remediated on 19.05.2025 (in MT) | Quantity remediated on 20.05.2025 (in MT) | Quantity remediated on 21.05.2025 (in MT) | Quantity remediated on 22.05.2025 (in MT) | Quantity remediated on 23.05.2025 (in MT) | Quantity remediated on 24.05.2025 (in MT) | Quantity remediated on 25.05.2025 (in MT) | Quantity remediated on 26.05.2025 (in MT) | Quantity remediated on 27.05.2025 (in MT) | Quantity remediated on 28.05.2025 (in MT) | Quantity remediated on 29.05.2025 (in MT) | Quantity remediated on 30.05.2025 (in MT) | Quantity remediated on 31.05.2025 (in MT) | Quantity remediated on 01.06.2025 (in MT) | Quantity remediated on 02.06.2025 (in MT) | Quantity remediated on 03.06.2025 (in MT) | Quantity remediated on 04.06.2025 (in MT) | Quantity remediated on 05.06.2025 (in MT) | Quantity remediated on 06.06.2025 (in MT) | Quantity remediated on 07.06.2025 (in MT) | Quantity remediated on 08.06.2025 (in MT) | Quantity remediated on 09.06.2025 (in MT) | Quantity remediated on 10.06.2025 (in MT) | Quantity remediated on 11.06.2025 (in MT) | Quantity remediated on 12.06.2025 (in MT) | Quantity remediated on 13.06.2025 (in MT) | Quantity remediated on 14.06.2025 (in MT) | Quantity remediated on 15.06.2025 (in MT) | Remarks | 30th April 2025 | 4th May 2025 | 5th May 2025 | 6th May 2025 | 7th May 2025 | 8th May 2025 | 1st May to 8th 2025 | Status
1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 10 | 11 | 12 | 13 | 14 | 16 | 16 | 17 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 17 | 16 | 16 | 16 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 17 | 15 | 16 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 15 | 15 | 16 | 17 | 21 | 24 | 25 |  | 26 | 27 | 28 | 20
M/s Tharuni Associates | M/s Tharuni Assosiates, Guntur | Kadapa Municipal Corporation | 1 | Kadapa | 400000 | 9046.83 | 390953.17 |  | 2800 | 3 | M1 | 900 | 45783 | 147 | 45930 |  |  |  |  | 1393.96 | 1393.96 | 1204.46 | [31 empty] | M1 functioning | 0 | [5 empty] | 0 | Work not yet started (Agency is awaiting for permission from municipality's to inauguration and start the work.)
|  | Kadapa Municipal Corporation | [8 empty] | M2 | 1100 | 45783 |  | 45930 | [38 empty] | M2 functioning
|  | Kadapa Municipal Corporation | [8 empty] | M3 | 800 | 45792 |  | 45930 | [38 empty] | M3 errection work is in progress
| M/s Tharuni Assosiates, Guntur | Rajahmundry, Cluster (3 ULBs) | 2 | Srikakulam | 80978 | 5056.39 | 75921.61 |  | 1500 | 2 | M4 | 800 | 45782 | 60 | 45843 |  |  |  |  | 376.715 | 376.715 | 429.655 | [31 empty] | M4 functional is slow due to bad weather conditions | [7 empty] | Work on Hold (Inauguration is Completeed )
[11 empty] | M5 | 700 | 45786 |  | 45843 | [38 empty] | M5 functional is slow due to bad weather conditions
|  | Rajahmundry, Cluster (3 ULBs) | 3 | Vizianagaram | 30604 | 9555.33 | 21048.67 |  | 800 | 1 | M6 | 800 | 45773 | 50 | 45838 |  |  |  |  | 661.21 | 661.21 | 117.1 | [31 empty] | M6 functioning
|  | Rajahmundry, Cluster (3 ULBs) | 4 | Rajahmundry | 76735 | 0 | 76735 |  | 1200 | 2 | M7 | 600 | 45792 | 70 | 45930 |  |  |  |  | 0 | 0 | o | [31 empty] | Weighbridge under installation
[11 empty] | M8 (M/c) | 600 | 45809 |  | 45930 | [38 empty] | M8 Machinery will be shifted from Gollaprolu
|  | Total |  |  | 188317 | 14611.72 | 173705.28 |  | 3500 | 5 | 0 | 2900 | 183133 | 180 | 183454 |  |  |  |  | 1037.925 | 1037.925 | 546.755 | [31 empty] | 0 | 0
| M/s Tharuni Assosiates, Guntur | Kakinada, Cluster (3 ULBs) | 5 | Kakinada | 300000 | 1346.59 | 298653.41 |  | 3400 | 3 | M9 | 900 | 45792 | 138 | 45930 |  |  |  |  | 233.16 | 233.16 | 212.31 | [31 empty] | Machinery under installation | [7 empty] | 1. Trail run Completed. 2.Processing of Legacy waste to be started.
|  | Kakinada, Cluster (3 ULBs) | [8 empty] | M10 | 1100 | 45782 |  | 45930 | [38 empty] | M10 is Functioning
|  | Kakinada, Cluster (3 ULBs) | [8 empty] | M11 | 1400 | 45797 |  | 45930 | [38 empty] | Machinery in transit & to be installed
|  | Kakinada, Cluster (3 ULBs) | 6 | Palacole | 30000 | 0 | 30000 |  | 600 | 1 | M19 | 600 | 45797 | 55 | 45930 |  |  |  |  | 0 | 0 | 0 | [31 empty] | Machinery under installation
|  | Kakinada, Cluster (3 ULBs) | 7 | Amalapuram | 27543 | 876.71 | 26666.29 |  | 600 | 1 | M12 | 600 | 45788 | 50 | 45930 |  |  |  |  | 354.83 | 354.83 | 335.21 | [31 empty] | M12 is Functioning | [7 empty] | Work not yet started (Agency is awaiting for permission from municipality's to inauguration and start the work.)
|  | Total |  |  | 357543 | 2223.3 | 355319.7 |  | 4600 | 5 | 0 | 4600 | 228956 | 243 | 229650 |  |  |  |  | 587.99 | 587.99 | 547.52 | [31 empty] | 0 | 0
| M/s Tharuni Assosiates, Guntur | Chilakaluripeta, Cluster (13 ULBs) | 8 | Chilakaluripet | 166278 | 0 | 166278 |  | 800 | 1 | M14 | 800 | 45792 | 120 | 45930 |  |  |  |  | 0 | 0 | 0 | [31 empty] | Electrical connections under progress
|  | Chilakaluripeta, Cluster (13 ULBs) | [6 empty] | 800 | 1 | M6(M/C) | 800 | 45853 |  | 45930 | [38 empty] | M/c will be shifted from Vizainagaram on 03.07.2025
|  | Chilakaluripeta, Cluster (13 ULBs) | 9 | Guntur | 43811 | 13017.24 | 30793.76 |  | 900 | 1 | M13 | 900 | 45756 | 40 | 45930 |  |  |  |  | 334.37 | 334.37 | 0 | [31 empty] | Work is in Progress
|  | Chilakaluripeta, Cluster (13 ULBs) | 10 | Narsaraopet | 30609 | 0 | 30609 |  | 600 | 1 | M17 (M/c) | 600 | 45823 | 60 | 45930 |  |  |  |  | 0 | 0 | 0 | [31 empty] | 1.M/c will be shifted from Jangareddigudem 2.Vinukonda Material(11195) will be shifted 01-07-205
|  | Chilakaluripeta, Cluster (13 ULBs) | [6 empty] | 1100 | 1 | M18 (M/c) | 1100 | 45853 |  | 45930 | [38 empty] | 1.M/c will be shifted from Ramachandrapuram 2.Piduguralla Material (10793) will be shifted to Narasaraopet from 01-07-2025
|  | Chilakaluripeta, Cluster (13 ULBs) | 11 | Bapatla | 46264 | 0 | 46264 |  | 1400 | 1 | M15 | 1400 | 45791 | 40 | 45838 |  |  |  |  | 0 | 0 | 0 | [31 empty] | Repalle material (7203) will be shifted to Bapatla from 15-06-2025
|  | Chilakaluripeta, Cluster (13 ULBs) | 12 | Macherla | 30894 | 0 | 30894 |  | 600 | 1 | M16 | 600 | 45802 | 60 | 45868 |  |  |  |  | 0 | 0 | 0 | [31 empty] | Dachepalli materia(6194)l will be shifted to Macherla from 15-07-2025 Gurazala material will be shifted to Macherla
|  | Chilakaluripeta, Cluster (13 ULBs) | 13 | Piduguralla | 10793 | 0 | 10793 |  |  |  | M17(s) | 600 | 01--7-2025 |  | 45930 |  |  |  |  | 0 | 0 | 0 | [31 empty] | Piduguralla Material will be shifted to Narasaraopet
|  | Chilakaluripeta, Cluster (13 ULBs) | 14 | Vinukonda | 11195 | 0 | 11195 |  |  |  | M17(s) | 600 | 01--7-2025 |  | 45930 |  |  |  |  | 0 | 0 | 0 | [31 empty] | Vinukonda qty will be shifted to Narasaraopet
|  | Chilakaluripeta, Cluster (13 ULBs) | 15 | Dachepalli | 6194 | 0 | 6194 |  |  |  | M16 (s) | 600 | 45853 | 15 | 45868 |  |  |  |  | 0 | 0 | 0 | [31 empty] | Dachepalli qty will be shifted to Macherla
|  | Chilakaluripeta, Cluster (13 ULBs) | 16 | Ponnuru | 8376 | 0 | 8376 |  |  |  | M13 (S) | 900 | 45829 | 10 | 45838 |  |  |  |  | 0 | 0 | 0 | [31 empty] | Ponnuru material will be shifted to Guntur
|  | Chilakaluripeta, Cluster (13 ULBs) | 17 | Repalle | 7203 | 0 | 7203 |  |  |  | M15 (S) | 1400 | 45823 | 10 | 45838 |  |  |  |  | 0 | 0 | 0 | [31 empty] | Repalle qty will be shifted to Bapatla
|  | Chilakaluripeta, Cluster (13 ULBs) | 18 | Gurazala | 1675 | 0 | 1675 |  |  |  | M16(s) | 600 | 45858 | 10 | 45868 |  |  |  |  | 0 | 0 | 0 | [31 empty] | Gurazala qty will be shifted to Macherla
|  | Chilakaluripeta, Cluster (13 ULBs) | 19 | Sattenapalle | 0 | 0 | 0 |  |  |  | - | [8 empty] | 0 | 0 | 0
|  | Chilakaluripeta, Cluster (13 ULBs) | 20 | Mangalagiri Tadepalli | 0 | 0 | 0 |  |  |  | - | [8 empty] | 0 | 0 | 0
| Total |  |  |  | 363292 | 13017.24 | 350274.76 |  | 6200 | 7 | 0 | 10900 | [7 empty] | 334.37 | 334.37 | 0 | [31 empty] | 0 | 0
| New Clusters Total |  |  |  | 1309152 | 38899.09 | 1270252.91 |  | 17100 | 20 | 0 | 19300 | [7 empty] | 3354.245 | 3354.245 | 2298.735
| M/s Tharuni Assosiates, Guntur | Cluster 01 | 1 | Yelamanchili | 8719 | 8719 | 0 | 100% | - | - | - | - | - | - | - |  |  |  |  | - | - | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work Completed | - | - | - | - | - | - | 0 | 0 | 0 | 0
|  |  | 2 | Pithapuram | 24910 | 24910 | 0 | 100% | - | - | - | - | - | - | - |  |  |  |  | - | - | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work Completed | - | - | - | - | - | - | 0 | 0 | 0 | 0
|  |  | 3 | Peddapuram | 19612 | 19612 | 0 | 100% | - | - | - | - | - | - | - |  |  |  |  | - | - | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work Completed | - | - | - | - | - | - | 0 | 0 | 0 | 0
|  |  | 4 | Rajam | 12849.14 | 12849.14 | 0 | 100% | - | - | - | - | 12.02.2025 | - | - |  |  |  |  | - | - | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work Completed | - | - | - | - | - | - | 0 | 0 | 0 | 0
|  |  | 5 | Tuni | 22097.82 | 22097.82 | 0 | 100% | 600 | - | M25 |  | 23.02.2025 | - | - |  |  |  |  | - | - | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work Completed.Machine Will be shifted to raychoti | - | - | - | - | - | - | 0 | 0 | 0 | 0
|  |  | 6 | Samalkot | 37786 | 37786 | 0 | 100% | - | - | - | - | 23.12.2024 | - | - |  |  |  |  | - | - | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work Completed | - | - | - | - | - | - | 0 | 0 | 0 | 0
|  |  | 7 | Bobbili | 14711 | 14711.13 | 0 | 100% | 600 | 1 | M24 | 600 | 18.02.2025 |  | 30.09.2025 | 0 | 0 | 0 | 121.15 | 121.15 | 121.15 | 0 |  | 362.55 | 505.47 | 0 | 494.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work Completed, Machine will be functioning for material shifting quantity | [6 empty] | 0 | 0 | 0 | 0
|  |  | 8 | Gollaprolu NP | 13135 | 13135 | 0 | 100% | 600 | 1 | M8 | 600 | 09.03.2025 |  | 31.05.2025 | 0 | 241.37 | 284.61 | 87.15 | 87.15 | 87.15 | 0 |  | 264.88 | 0 | 0 | 256.65 | 0 | 150.38 |  |  | 0 | 0 | 0 | 306.21 | 342.75 | 0 | 528.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work process Completed.Machine will be shifted to rajahmundry | [6 empty] | 0 | 181.53 | 262.03 | 0
|  |  | 9 | Amadalavalasa | 6678.68 | 0 | 6678.68 | 0% |  |  | M4(S) |  | 01.08.2025 | 15 | 15.08.2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Amadalavalasa material 6679MT will be shifted to Srikakulam |  |  | #VALUE! | 2025-09-30 | Qty will be Shifted to Srikakulam |  | 0 | 0 | 0 | 0
|  |  | 10 | Ichapuram | 6260 | 0 | 6260 | 0% |  |  | M4(S) |  | 01.09.2025 | 15 | 15.09.2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Ichapuram material 6260MT will be shifted to Srikakulam |  |  | #VALUE! | 2025-09-30 | Qty will be Shifted to Srikakulam |  | 0 | 0 | 0 | 0
|  |  | 11 | Palasa -Kasibugga | 9625.88 | 0 | 9625.88 | 0% |  |  | M4(S) |  | 01.08.2025 | 20 | 20.08.2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Palasa material 9626MT will be shifted to Srikakulam |  |  | #VALUE! | 2025-09-30 | Qty will be Shifted to Srikakulam |  | 0 | 0 | 0 | 0
|  |  | 12 | Parvathipuram | 11921.09 | 0 | 11921.09 | 0% |  |  | M24(S) |  | 01.07.2025 | 20 | 20.07.2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Parvathipuram material 11921MT will be shifted to Bobbili | [6 empty] | 0 | 0 | 0 | 0
|  |  | 13 | Salur | 12042 | 0 | 12042 | 0% |  |  | M24(S) |  | 15.08.2025 | 20 | 05.09.2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Salur material12042MT will be shifted to Bobbili | [6 empty] | 0 | 0 | 0 | 0
|  |  | 14 | Palakonda | 7700 | 0 | 7700 | 0% |  |  | M4(S) |  | 15.07.2025 | 20 | 05.08.2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Palakonda material 7700MT will be shifted to Srikakulam |  |  | #VALUE! | 2025-09-30 | Qty will be Shifted to Srikakulam |  | 0 | 0 | 0 | 0
|  |  | 15 | Nellimarla | 7727.4 | 0 | 7727.4 | 0% |  |  | M6(S) |  | 2025-07-01 | 20 | 2025-07-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Nellimarla material 7727MT will be shifted to Vizainagaram |  |  | -1 | 2025-06-30 | Qty will be Shifted to Vizianagaram |  | 0 | 0 | 0 | 0
|  |  | 16 | Narsipatnam | 6250 | 0 | 6250 | 0% |  |  | M25(S) |  | 2025-08-01 | 30 | 2025-08-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Due to no Vehicle movement acess from Narsipatnam to Tuni , Tuni machinery will be shifted to Raychoti |  |  |  | 15.06.2025 |  |  | 0 | 0 | 0 | 0 | [5 empty] | Narsipatnam Material will be shifted to Tuni
[5 empty] | 222025.01 | 153820.09 | 68205.05 | 69.28% | 1800 | 2 | 0 | 1200 |  |  |  | 0 | 241.37 | 284.61 | 208.3 | 208.3 | 208.3 | 0 |  | 627.43 | 505.47 | 0 | 750.88 | 0 | 150.38 | 0 | 0 | 0 | 0 | 0 | 306.21 | 342.75 | 0 | 930.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | #VALUE! | 229558 | 0 | 0 | 0 | 181.53 | 262.03 | 0 | 0 | 0 | 0 | 0 | 0
| M/s Tharuni Assosiates, Guntur | Cluster 02 | 17 | Nidadavole | 37207.27 | 37207.27 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 02 | 18 | Tanuku | 74206 | 74206 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 02 |  | Kovvur | 8775.13 | 8775.13 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 02 |  | Amalapuram | 27910.22 | 27910.22 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 02 | 19 | Ramachandra-puram | 22142.68 | 5980 | 16162.68 | 27.01% | 1100 | 1 | M18 | 1100 | 02.04.2025 |  | 01.07.2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439 | 0 | 0 | 0 | 0 | 0 | 0 | 686.01 | 0 | 696.27 | 600.22 | Work in progress with previous material | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 02 | 20 | Yeleswaram | 11022 | 0 | 11022 | 0% |  |  | M11(S) |  | 15.08.2025 | 20 | 05.09.2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yelleswaram material11022MT will be shifted to Kakinada |  |  |  | 15.06.2025 |  |  | 0 | 0 | 0 | 0 | [5 empty] | Yelleswaram Material will be shifted to Samalkota
|  | Cluster 02 | 21 | Mandapeta | 8779 | 0 | 8779 | 0% | 400 |  | M28 | 400 | 01.07.2025 | 30 | 30.07.2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Machine arrived at Site on 10-06-2025 | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 02 | 22 | Mummidivaram | 5624 | 0 | 5624 | 0% |  |  | M12(S) |  | 2025-09-15 | 15 | 2025-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Mumidivaram material5624 MT will be shifted to Amalapuram |  |  | 15 | 2025-09-30 | Qty will be Shifted to Amalapuram |  | 0 | 0 | 0 | 0
[5 empty] | 195666.3 | 154078.62 | 41587.68 | 78.75% | 1500 | 1 | 0 | 1500 |  | 65 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439 | 0 | 0 | 0 | 0 | 0 | 0 | 686.01 | 0 | 696.27 | 600.22 |  | 0 | 0 | 15 | 45930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Avinash Agency | Cluster 03 | 23 | YSR Tadigadapa | 50000 | 50000 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 | 24 | Tiruvuru | 20842 | 20842 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 |  | Nuzvid | 15995 | 15995 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 |  | Kondapalli | 4925 | 4925 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 |  | Palacole | 25181 | 25181 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 | 25 | Jangareddy-gudem | 18736 | 18736 | 0 | 100% | 600 | 1 | M17 | 600 | 23.02.2025 |  | 10.06.2025 | 267.82 | 174.46 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 356.96 | 383.94 | 173.21 | 0 | 494.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work Completed, Machine wiil be functioning for material shifting quantity | [6 empty] | 0 | 210.47 | 0 | 0
|  | Cluster 03 | 26 | Narsapur | 51312 | 46196.1 | 5115.9 | 90.03% | 600 | 1 | M27 | 600 | 15.11.2024 |  | 30.09.2025 | 0 | 0 | 496.68 | 564.87 | 564.87 | 564.87 | 545.09 |  | 532.33 | 412.24 | 0 | 0 | 0 | 0 | 0 | 474.44 | 158.84 | 293.33 | 335.27 | 0 | 327.87 | 348.36 | 348.36 | 474.22 | 348.91 | 529.51 | 311.62 | 435.93 | 0 | 479.63 | 0 | 0 | 0 | 484.9 | 0 | 535.2 | 0 | 0 | Work in progress with previous material |  |  |  | 15.07.2025 |  |  | 394.4 | 562.24 | 510.27 | 0 | [5 empty] | Work in progress
|  | Cluster 03 | 27 | Akiveedu | 7312 | 0 | 7312 | 0% |  |  | M21(S) |  | 15.09.2025 | 15 | 30.09.2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Akiveedu material7312MT will be shifted to Bhimavaram |  |  | #VALUE! | 2025-09-30 |  |  | 0 | 0 | 0 | 0
|  | Cluster 03 | 28 | Chintalapudi | 7300 | 0 | 7300 | 0% |  |  | M17(S) |  | 01.08.2025 | 10 | 10.08.2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Chintalapudi material 7300MT will be shifted to Jangareddy Gudem | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 | 29 | Vuyyuru | 10000 | 0 | 10000 | 0% |  |  | M27M/c |  | 25.07.2025 | 20 | 15.08.2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | M27M/c Will be Shifted from Narsapur from 15-07-2025 |  |  |  | 31.07.2025 |  |  | 0 | 0 | 0 | 0 | [5 empty] | Vuyyuru material will be shifted to Pedana
|  | Cluster 03 | 30 | Pedana | 5821 | 0 | 5821 | 0% |  | 1 | M27(S) |  | 16.08.2025 | 25 | 30.08.2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pedana material 5821Mt will be shifted to Vuyyuru |  |  |  | 30.06.2025 |  |  | 0 | 0 | 0 | 0 | [5 empty] | Erection Work in Progress
[5 empty] | 217424 | 181875.1 | 35548.9 | 83.65% | 1200 | 3 | 0 | 1200 | 0 |  | 0 | 267.82 | 174.46 | 496.68 | 564.87 | 564.87 | 564.87 | 545.09 |  | 532.33 | 412.24 | 0 | 0 | 0 | 0 | 0 | 474.44 | 158.84 | 293.33 | 692.23 | 383.94 | 501.08 | 348.36 | 842.83 | 474.22 | 348.91 | 529.51 | 311.62 | 435.93 | 0 | 479.63 | 0 | 0 | 0 | 484.9 | 0 | 535.2 | 0 | 0 |  | 0 | 0 | #VALUE! | 45930 | 0 | 0 | 394.4 | 772.71 | 510.27 | 0 | 0 | 0 | 0 | 0 | 0
|  | Old clusters Total |  |  | 635115.31 | 489773.81 | 145341.5 | 77.12% | 4500 | 6 | 7 | 3900 |  |  |  | 267.82 | 415.83 | 781.29 | 773.17 | 773.17 | 773.17 | 545.09 |  | 1159.76 | 917.71 | 0 | 750.88 | 0 | 150.38 | 0 | 474.44 | 158.84 | 293.33 | 692.23 | 690.15 | 843.83 | 348.36 | 1773.66 | 474.22 | 348.91 | 529.51 | 311.62 | 874.93 | 0 | 479.63 | 0 | 0 | 0 | 484.9 | 686.01 | 535.2 | 696.27 | 600.22 |  | 0 | 0 | #VALUE! | 321418 | 0 | 0 | 394.4 | 954.24 | 772.3 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grand Total |  |  | 1944267.31 | 528672.9 | 1415594.41 | 27.19% | 21600 | 26 | 7 | 23200 | [7 empty] | 4127.415 | 4127.415 | 2843.825

## Sudhakar (2)
Agency Wise Legacy Waste Details
Agency Name | Cluster | S. No. | ULB | Quantity to be remediated in MT | Cumulative Quantity remediated till date in MT | Balance Quantity in MT | % of Comp. | Capacity of Machine per day to be installed (in MT) | No of Machines | Details of Machinery |  |  |  |  | Quantity remediated on 14.05.2025 (in MT) | Quantity remediated on 15.05.2025 (in MT) | Quantity remediated on 16.05.2025 (in MT) | Quantity remediated on 13.05.2025 (in MT) | Quantity remediated on 12.05.2025 (in MT) | Difference b/n Col.11 & Col.15 | Quantity remediated on 21.05.2025 (in MT) | Quantity remediated on 17.05.2025 (in MT) | Quantity remediated on 18.05.2025 (in MT) | Quantity remediated on 19.05.2025 (in MT) | Quantity remediated on 20.05.2025 (in MT) | Quantity remediated on 21.05.2025 (in MT) | Quantity remediated on 22.05.2025 (in MT) | Quantity remediated on 23.05.2025 (in MT) | Quantity remediated on 24.05.2025 (in MT) | Quantity remediated on 25.05.2025 (in MT) | Quantity remediated on 26.05.2025 (in MT) | Quantity remediated on 27.05.2025 (in MT) | Quantity remediated on 28.05.2025 (in MT) | Quantity remediated on 29.05.2025 (in MT) | Quantity remediated on 30.05.2025 (in MT) | Quantity remediated on 31.05.2025 (in MT) | Quantity remediated on 01.02.2025 (in MT) | Quantity remediated on 02.02.2025 (in MT) | Quantity remediated on 03.06.2025 (in MT) | Quantity remediated on 04.06.2025 (in MT) | Quantity remediated on 05.06.2025 (in MT) | Quantity remediated on 06.06.2025 (in MT) | Quantity remediated on 07.06.2025 (in MT) | Quantity remediated on 08.06.2025 (in MT) | Quantity remediated on 09.06.2025 (in MT) | Quantity remediated on 10.06.2025 (in MT) | Quantity remediated on 11.06.2025 (in MT) | Quantity remediated on 12.06.2025 (in MT) | Quantity remediated on 13.06.2025 (in MT) | Quantity remediated on 14.06.2025 (in MT) | Quantity remediated on 15.06.2025 (in MT) | Remarks
[10 empty] | No. Machines | Daily capacity | Start date | No. of days | Expected date of completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 10 | 11 | 12 | 13 | 14 | 16 | 16 | 17 | 16 | 16 | 17 | 17 | 16 | 16 | 16 | 16 | 17 | 16 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 17 | 17 | 17 | 15 | 16 | 15 | 15 | 16 | 15 | 16 | 15 | 15 | 16 |  | 15 | 16 | 17
M/s Sudhakar Infra Pvt.Ltd. | Tenali | 1 | Tenali | 63550 | 63550 | 0 | 100% | 1300 | 2 | M1 | 650 | 10.02.2025 | 20 | 08.06.2025 | 936.32 | 767 | 0 | 944.11 | 896.94 |  |  | 485.33 | 582.88 | 800.16 | 0 | 0 | 0 | 836.52 | 160.26 | 927.64 | 906.95 | 873.77 | 941.03 | 834.03 | 890.14 | 834.89 | 890.27 | 925.66 | 926.74 | 678.98 | 950.54 | 739.61 | 178 | 0 | 0 | 0 | 0 | 0 |  |  |  | As per tender Quantity is remediated,But disposal of remediated waste is Pending
[10 empty] | M2 | 650
Total |  |  |  | 63550 | 63550 | 0 | 100% | 1300 | 2 | [5 empty] | 936.32 | 767 | 0 | 944.11 | 896.94 |  |  | 485.33 | 582.88 | 800.16 | 0 | 0 | 0 | 836.52 | 160.26 | 927.64 | 906.95 | 873.77 | 941.03 | 834.03 | 890.14 | 834.89 | 890.27 | 925.66 | 926.74 | 678.98 | 950.54 | 739.61 | 178 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
6

## Sudhakar (hidden)
ULB | Quantity to be remediated in MT | Cumulative Quantity remediated till date in MT | Quantity remediated upto 30th April 2025 in MT | Balance Quantity in MT | Capacity of Machine per day to be installed (in MT) | No of Machines | Details of Machinery |  |  | Remarks | 30th April 2025 (Qty in MT) | 1st May 2025 Qty in MT | 2nd May 2025 Qty in MT | 3rd May 2025 Qty in MT | 4th May 2025 Qty in MT | 5th May 2025 Qty in MT | 6th May 2025 Qty in MT | 7th May 2025 Qty in MT | 8th May 2025 Qty in MT | 1st to 8th May 2025 Qty in MT | Status
[7 empty] | No. Machines | Daily capacity | Starting date
M/s Sudhakar Infra Pvt.Ltd.
Tenali | 63550 | 41388.45 | 39685.25 | 22161.55 | 1000 | 2 | M1&M2 | 1000 | 10.02.2025 |  | 905.48 | 0 | 864.15 | 839.05 | [5 empty] | 1703.2